## Fit-Out Material RFI
WOOD COUTURE | WOOD COUTURE | K5M · FIT-OUT MATERIAL RFI | [6 empty] | PROJECT: K5M ¦ DOCUMENT: K5M-FIT-MAT-RFI-01
WOOD COUTURE | WOOD COUTURE | [7 empty] | STATUS: DRAFT – INTERNAL REVIEW ¦ ISSUE DATE: 21 JUL 2026
WOOD COUTURE | WOOD COUTURE | [7 empty] | BASIS: G&B MATERIAL LIST 21.07.2026 ¦ SCOPE: AWARDED FIT-OUT BOQ ONLY
Scope note: This register is limited to material-code and material-application clarifications affecting awarded Fit-Out BOQ tasks. Hardware, installation methodology, quantities, non-awarded materials, wallpaper and carpet are excluded.
OPEN MATERIAL CLARIFICATIONS
RFI No. | Affected BOQ Task(s) | Area | Client BOQ Task / Material Application | BOQ Material Code(s) | DD-100 Drawing Ref. / Page | Latest G&B / DD-100 Information | Material Conflict / Our Understanding | Clarification Requested from G&B | G&B Response | Status | Date Raised | Response Date
FM-001 | A/2, A/4, A/7, C/7 | Entrance & Bedroom | Plinthe en bois / wood skirting; arche en bois / wooden arch; porte en bois / wooden door; tablette en bois / wooden shelf | A-WD-01d; A-WD-01; A-WD-01b | ET01-T1B1-ENT-200 / p.8; ET01-T1B1-ENT-302 / p.11; ET01-T1B1-CHA-200 / p.58 | DD-100 identifies these applications as A-WD-01b. The 21.07.2026 material list replaces A-WD-01b walnut with medium-stained oak, colour matching parquet A-WD-04b. | The awarded BOQ uses three code variants for connected applications: A-WD-01d, generic A-WD-01 and A-WD-01b. | Please confirm the correct material code for each listed BOQ task and whether all four applications shall follow A-WD-01b in medium-stained oak matching A-WD-04b. |  | Open | 2026-07-21
FM-002 | A/3, B/7, B/8, B/9, B/10, B/11, C/4 | Entrance, Bathroom & Bedroom | Stone arches, bathroom benches, WC shelf, vanity top and bedroom arch | A-ST-07a | ET01-T1B1-SDB-100 / p.24; SDB-312 / p.44; SDB-313 / p.45; SDB-315 / p.47; CHA-120 / p.55 | The 21.07.2026 list shows A-ST-07a honey onyx and a subsequent row stating ‘Replaced by Taj Mahal’, polished. | The same code is shown twice, retaining the superseded honey-onyx row as well as the replacement row. | Please confirm that polished Taj Mahal is the final material for A-ST-07a across all affected BOQ tasks and that honey onyx no longer applies. |  | Open | 2026-07-21
FM-003 | A/8 | Entrance | Double pivot doors – handle material/finish only | A-ME-02i | ET01-T1B1-ENT-200 / p.8; ENT-304 / p.13; ENT-311 / p.20; ENT-312 / p.21 | DD-100 identifies the handles as A-ME-02i. The 21.07.2026 material list retains A-ME-02i (dark hammered patinated brass, matt varnish) but removes all locations. | The material remains listed, but its use on the pivot-door handles is no longer confirmed by the location column. | Please confirm whether the handles under BOQ task A/8 shall retain material/finish A-ME-02i. This query excludes handle design and hardware selection. |  | Open | 2026-07-21
FM-004 | B/4(a), B/4(b) | Bathroom – Shower & WC | Revêtement mural en pierres / stone wall cladding | A-ST-01c | ET01-T1B1-SDB-100 / p.24; SDB-200 / p.30; SDB-201 / p.31 | DD-100 calls up A-ST-01c for the bathroom stone walls. The updated material list identifies A-ST-01c for bathroom arches and niche but does not state wall cladding. | The BOQ and DD-100 application is broader than the locations shown in the latest material list. | Please confirm that A-ST-01c remains applicable to the shower and WC stone wall cladding under B/4(a) and B/4(b). |  | Open | 2026-07-21
FM-005 | B/5 | Bathroom – Shower & WC | Seuil en pierre / stone threshold at bathroom opening | BOQ: A-ST-01d; DD-100: A-ST-01c | ET01-T1B1-SDB-311 / p.43; SDB-309 / p.41; SDB-312 / p.44 | The latest material list limits A-ST-01d to the shower floor and identifies A-ST-01c for the bathroom arches. DD-100 shows the opening surround as A-ST-01c. | The awarded BOQ specifies A-ST-01d for the threshold, which conflicts with the updated material locations and door-opening details. | Please confirm the correct stone material code for the threshold/opening under B/5: A-ST-01d, A-ST-01c, or another code. |  | Open | 2026-07-21
FM-006 | B/8 | Bathroom | Stone bench including metal structure and base | A-ST-07a + A-ME-01a | ET01-T1B1-SDB-315 / p.47; SDB-316 / p.48 | DD-100 identifies the bench top as A-ST-07a and the traverse/base as A-ME-01a. The latest material list assigns A-ME-01a to bathroom handles and door surrounds only. | The material schedule does not confirm A-ME-01a for the exposed bench structure and base. | Please confirm whether the bench structure, traverse and base under B/8 shall be finished in A-ME-01a mirror-polished stainless steel. |  | Open | 2026-07-21
FM-007 | B/12 | Bathroom | Niche en pierre / stone niche | BOQ: A-ST-07a; DD-100 / material list: A-ST-01c | ET01-T1B1-SDB-100 / p.24; SDB-304 / p.36; SDB-306 / p.38 | The awarded BOQ identifies the niche as A-ST-07a. DD-100 and the updated material-list location identify the bathroom niche as A-ST-01c. | The BOQ material code conflicts with both the drawings and the latest material list. | Please confirm the final stone material code for the niche under B/12: A-ST-07a (Taj Mahal) or A-ST-01c (light beige stone, honed). |  | Open | 2026-07-21
FM-008 | C/1 | Bedroom | Revêtement sol en parquet bois / timber parquet flooring | BOQ: A-WD-04d; DD-100 / material list: A-WD-04b | ET01-T1B1-CHA-100 / p.53; CHA-120 / p.55; CHA-300 / p.60 | DD-100 uses A-WD-04b. The 21.07.2026 list replaces A-WD-04b dark-stained oak parquet with medium-stained oak parquet, Hakwood reference Idéal. | A-WD-04d does not appear in DD-100 or the updated material list. | Please confirm that BOQ task C/1 shall follow A-WD-04b and the updated Hakwood Idéal medium-stained oak parquet specification. |  | Open | 2026-07-21
FM-009 | C/2 | Bedroom | Plinthe en pierre / stone skirting | BOQ / DD-100: A-ST-01c; updated list: A-ST-01e and A-ST-02c | ET01-T1B1-CHA-120 / p.55; CHA-200 / p.58; CHA-301 / p.61 | The BOQ and DD-100 identify bedroom skirting as A-ST-01c. The updated material list assigns bedroom skirting to both A-ST-01e and A-ST-02c, while A-ST-01c is listed for the bedroom threshold. | Three material codes now indicate conflicting applications for the bedroom skirting. | Please confirm the final material code(s) for the bedroom skirting under C/2 and, if both A-ST-01e and A-ST-02c apply, identify their respective locations/distribution. |  | Open | 2026-07-21
FM-010 | C/3 | Bedroom | Stone threshold including metal joint | BOQ: A-ST-01c + A-ME-02c; DD-100: A-ST-01c + A-ME-02h | ET01-T1B1-CHA-120 / p.55; CHA-300 / p.60 | DD-100 identifies the threshold stone as A-ST-01c and the joint as A-ME-02h. A-ME-02c does not appear in the latest material list. | The metal-joint code in the BOQ differs from DD-100 and is absent from the governing material schedule. | Please confirm the final material/finish code for the metal joint under C/3: A-ME-02h, A-ME-02c, or another code. |  | Open | 2026-07-21
FM-011 | C/6 | Bedroom | Panneaux muraux en boiserie / timber wall panelling | A-WD-02c | ET01-T1B1-CHA-120 / p.55; CHA-200 / p.58; CHA-301 / p.61; CHA-302 / p.62 | DD-100 identifies the bedroom wall panelling as A-WD-02c. The latest material-list location mentions A-WD-02c for the bedroom banquette, but not the wall panelling. | The drawing application is not explicitly included in the updated material-list locations. | Please confirm that the wall panelling under C/6 shall use A-WD-02c, white-cerused oak with matt finish. |  | Open | 2026-07-21
FM-012 | B/2 | Bathroom – Shower | Revêtement sol en pierres / shower stone flooring | A-ST-01d | ET01-T1B1-SDB-100 / p.24; SDB-120 / p.26; SDB-300 / p.32 | The latest material list specifies A-ST-01d as light beige stone with an anti-slip finish, but no anti-slip classification or approved benchmark is stated. | The required anti-slip characteristic is stated but not defined sufficiently for material selection. | Please confirm the required anti-slip classification or approved finish benchmark for A-ST-01d under B/2. |  | Open | 2026-07-21