Dear All,

Please find below the overall project report for K5M as of 31 July.

1. Materials (FF&E + Fit-Out)

- Material package finalized for both FF&E and Fit-Out

- Meeting held with H&T/Cathy to review the full list and process

- Meeting minutes shared earlier

- Three open RFIs with the client design team were closed today

2. Fit-Out Scope

- Client architect has closed the Fit-Out RFI from their side

- Client has confirmed their understanding of our scope

- One internal RFI has been raised and should be closed as soon as possible

3. FF&E Shop Drawings

- Feedback on SHD Version 00 has now been fully received from both the client design team and the supplier

- Consolidation into SHD Version 01 is now in progress

4. 3D Model

- Work on the model build has started

5. Open Items for Next Week

- Clarify artwork responsibility with the client

- Request outstanding compliance documents from the client, including electrical, stone, and hardware compliance, and any other categories they may flag

6. COC / Tooling / Project Systems

- Continuing the transition to Claude Code for K5M maintenance

- The system is now supporting a significant part of day-to-day project coordination

- Dedicated K5M Task Tracker has been created

- Project Calendar v2 has been finalized

- Both are managed through my AI system

7. Risk Mitigation

- H&T communication and timeline alignment need to remain a priority

- Fit-Out BOQ scope gap needs to be closed

- Client substructure detailing for the Fit-Out contractor needs to be sent as soon as possible, as it may affect white box readiness

8. Important Dates

- 3 August: BOQ scope gap meeting with all stakeholders

- 5 August: Substructure requirement list to client

- 6 August: Fit-Out SHD 01 begins; lighting designer RFI must close

- 8 / 10 August: Round 1 sample box dispatch / must reach Dubai office

- 18 August: Physical sample box sent to clients in Morocco and Paris

- 20 August: SHD Version 01 sent to Paris team for feedback

- 31 August: Onsite survey visit

Please let me know if any further clarification is required.

Regards,
Shagun