## Data
K5M — PROJECT CALENDAR — SOURCE DATA
Client |  | Supplier |  | WDCO Internal PM |  | Deadline (red border)
v2 — 29 July 2026. One-off activities above the recurring-rule rows at the bottom. Recurring tasks need only one row (Recurs/Weekday/Until filled in) — they expand automatically onto the month tabs, not as individual rows here.
Start | End | Category | Activity | Notes | Is Deadline | Recurs | Recurs Weekday | Recurs Until
2026-07-15 |  | Client | Project kick-off | Milestone. | Y
2026-07-15 |  | WDCO Internal PM | G&B office unavailable 1-24 Aug | Informed at kick-off meeting. | N
2026-07-16 | 2026-07-22 | Client | First RFI and FF&E SHD V00 issue | Issued within 7 days of kick-off. | N
2026-07-17 |  | WDCO Internal PM | White-box availability confirmed as 30 Aug | Was assumed immediate before. | N
2026-07-22 | 2026-07-28 | Supplier | SHD V00 parallel review & feedback | 28 Jul is the hard feedback deadline. | Y
2026-07-23 | 2026-07-29 | Client | FF&E SHD V00 parallel review & feedback |  | N
2026-07-27 |  | Supplier | Material scope issued to Production Partner | Milestone. | Y
2026-07-27 | 2026-08-07 | Supplier | Round 1 sample-box development | 12 calendar days. | N
2026-07-29 | 2026-08-04 | Supplier | SHD V01 drafting and issue |  | N
2026-07-30 | 2026-08-03 | Client | FF&E SHD V01 drafting | Developed while G&B review unavailable. | N
2026-07-30 |  | Client | Fit-out RFI closure | Milestone. | Y
2026-07-31 | 2026-08-20 | Supplier | Fit-Out SHD Version 00 | Prepared from available architectural info. | N
2026-08-03 | 2026-08-21 | Client | Fit-out SHD V00 & preliminary material package |  | N
2026-08-05 | 2026-08-11 | Supplier | SHD V01 parallel review & feedback | Only controlled final coordination follows. | N
2026-08-08 | 2026-08-10 | Supplier | Dispatch/delivery Round 1 sample box to Dubai | Must reach WDCO Dubai by 10 Aug. | Y
2026-08-11 | 2026-09-10 | Supplier | Feedback round & final approved material box | Close by 10 Sept. | N
2026-08-12 | 2026-09-10 | Supplier | Signed GFP SHD Version 02 | Required before production release. | Y
2026-08-24 |  | Client | G&B team availability resumes | Office unavailable 1-24 Aug. | Y
2026-08-24 | 2026-08-28 | Client | FF&E SHD V01 & Material Package review | Formal parallel review resumes 24 Aug. | N
2026-08-24 | 2026-08-28 | Client | Fit-out SHD V00 review & agreement in principle | Assumes approval from Architect office. | N
2026-08-25 | 2026-09-15 | WDCO Internal PM | Site holiday period (Mawlid) | Open confirmation: is site accessible for the 31 Aug survey despite this? | N
2026-08-31 | 2026-09-02 | Client | FF&E SHD V02 drafting | Final drafting after V01 feedback. | N
2026-08-31 |  | Client | Fit-out site survey | Planned once white box is ready. | N
2026-08-31 |  | Supplier | Site visit / measurement | Milestone. | N
2026-09-01 | 2026-09-04 | Client | Fit-out site-survey report | 3-4 working days after survey. | N
2026-09-01 | 2026-09-03 | Supplier | Site survey report | Issued by 3 Sept. | N
2026-09-03 | 2026-09-08 | Client | Signed FF&E SHD V02 & confirmed material package | Production starts only after this. | Y
2026-09-04 | 2026-09-10 | Supplier | Fit-Out SHD V01 incorporating survey |  | N
2026-09-07 | 2026-09-15 | Client | Fit-out SHD V01 revisions | Site-survey findings incorporated. | N
2026-09-09 | 2026-10-23 | Client | FF&E mock-up production, QC and packing |  | N
2026-09-10 | 2026-10-09 | Supplier | FF&E production | Begins only after signed GFP SHD. | N
2026-09-10 |  | Supplier | Signed GFP Fit-Out SHD | Required before production starts. | Y
2026-09-10 | 2026-09-24 | Supplier | Fit-Out production |  | N
2026-09-16 | 2026-09-21 | Client | Fit-out SHD V01 & material-package approval | Final fit-out production-release gate. | Y
2026-09-22 | 2026-10-16 | Client | Fit-out production, QC and packing |  | N
2026-10-10 | 2026-11-28 | Supplier | Packing, dispatch, sea freight, customs, delivery | Both packages together. | N
2026-10-25 |  | Client | Combined dispatch on next available sailing | Milestone. | Y
2026-10-25 | 2026-12-03 | Client | Sea freight to Casablanca |  | N
2026-11-15 |  | WDCO Internal PM | Internal working deadline | Supplier's 15 Dec hard deadline is unconfirmed; treat 15 Nov as the real internal target. | Y
2026-11-29 | 2026-12-13 | Supplier | Fit-Out and FF&E installation |  | N
2026-12-03 | 2026-12-07 | Client | Customs, port release, delivery to site |  | N
2026-12-04 | 2026-12-18 | Client | Fit-out installation | Precedes FF&E installation. | N
2026-12-14 |  | Supplier | Ready for site inspection | All contracted installation complete. | Y
2026-12-15 |  | Supplier | Hard deadline (as communicated to supplier) | Tentative, not yet confirmed. | Y
2026-12-19 | 2026-12-20 | Client | FF&E installation |  | N
2026-12-20 |  | Client | Complete T1B1 mock-up ready for inspection | Indicative revised readiness date. | Y
2026-07-31 |  | Client | Send project update to client-facing group | Recurring — biweekly, anchored 31 Jul 2026. | N | Biweekly | Friday | 2026-12-31
2026-07-31 |  | WDCO Internal PM | Send project update to internal WDCO K5M group | Recurring — weekly, anchored 31 Jul 2026. | N | Weekly | Friday | 2026-12-31

## Jul 2026
K5M — JULY 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  |  | 1 | 2 | 3 | 4
5 | 6 | 7 | 8 | 9 | 10 | 11
12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  | ⚑ Project kick-off | First RFI and FF&E SHD V00 issue
|  |  | G&B office unavailable 1-24 Aug |  | White-box availability confirmed as 30 Aug
19 | 20 | 21 | 22 | 23 | 24 | 25
First RFI and FF&E SHD V00 issue |  |  |  | FF&E SHD V00 parallel review & feedback
⚑ SHD V00 parallel review & feedback
26 | 27 | 28 | 29 | 30 | 31
FF&E SHD V00 parallel review & feedback |  |  |  | FF&E SHD V01 drafting
⚑ SHD V00 parallel review & feedback |  |  | SHD V01 drafting and issue
Round 1 sample-box development
| ⚑ Material scope issued to Production Partner |  |  | ⚑ Fit-out RFI closure | Fit-Out SHD Version 00
Send project update to client-facing group
Send project update to internal WDCO K5M group

## Aug 2026
K5M — AUGUST 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
1
FF&E SHD V00 parallel review & feedback |  |  |  | FF&E SHD V01 drafting
⚑ SHD V00 parallel review & feedback |  |  | SHD V01 drafting and issue
Round 1 sample-box development
| ⚑ Material scope issued to Production Partner |  |  | ⚑ Fit-out RFI closure | Fit-Out SHD Version 00
Send project update to client-facing group
Send project update to internal WDCO K5M group
2 | 3 | 4 | 5 | 6 | 7 | 8
Fit-Out SHD Version 00
Round 1 sample-box development | [5 empty] | ⚑ Dispatch/delivery Round 1 sample box to Dubai
SHD V01 drafting and issue |  |  | SHD V01 parallel review & feedback
FF&E SHD V01 drafting |  |  |  |  | Send project update to internal WDCO K5M group
Fit-out SHD V00 & preliminary material package
9 | 10 | 11 | 12 | 13 | 14 | 15
Fit-out SHD V00 & preliminary material package
Fit-Out SHD Version 00
SHD V01 parallel review & feedback |  |  | ⚑ Signed GFP SHD Version 02
⚑ Dispatch/delivery Round 1 sample box to Dubai |  | Feedback round & final approved material box
Send project update to client-facing group
Send project update to internal WDCO K5M group
16 | 17 | 18 | 19 | 20 | 21 | 22
Feedback round & final approved material box
⚑ Signed GFP SHD Version 02
Fit-out SHD V00 & preliminary material package
Fit-Out SHD Version 00 |  |  |  |  | Send project update to internal WDCO K5M group
23 | 24 | 25 | 26 | 27 | 28 | 29
Feedback round & final approved material box
⚑ Signed GFP SHD Version 02
FF&E SHD V01 & Material Package review
Fit-out SHD V00 review & agreement in principle
| ⚑ G&B team availability resumes | Site holiday period (Mawlid)
Send project update to client-facing group / +1 more (see Data tab)
30 | 31
Feedback round & final approved material box
⚑ Signed GFP SHD Version 02
Site holiday period (Mawlid)
| FF&E SHD V02 drafting |  |  | ⚑ Signed FF&E SHD V02 & confirmed material package
| Fit-out site survey | Fit-out site-survey report
| Site visit / measurement | Site survey report |  |  | Fit-Out SHD V01 incorporating survey / +1 more (see Data tab)

## Sep 2026
K5M — SEPTEMBER 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  | 1 | 2 | 3 | 4 | 5
Feedback round & final approved material box
⚑ Signed GFP SHD Version 02
Site holiday period (Mawlid)
| FF&E SHD V02 drafting |  |  | ⚑ Signed FF&E SHD V02 & confirmed material package
| Fit-out site survey | Fit-out site-survey report
| Site visit / measurement | Site survey report |  |  | Fit-Out SHD V01 incorporating survey / +1 more (see Data tab)
6 | 7 | 8 | 9 | 10 | 11 | 12
Site holiday period (Mawlid)
Feedback round & final approved material box |  |  |  |  | Send project update to client-facing group
⚑ Signed GFP SHD Version 02 |  |  |  |  | Send project update to internal WDCO K5M group
Fit-Out SHD V01 incorporating survey
⚑ Signed FF&E SHD V02 & confirmed material package |  |  | FF&E mock-up production, QC and packing
Fit-out SHD V01 revisions
13 | 14 | 15 | 16 | 17 | 18 | 19
FF&E mock-up production, QC and packing
FF&E production
Fit-Out production
Fit-out SHD V01 revisions |  |  | ⚑ Fit-out SHD V01 & material-package approval
Site holiday period (Mawlid) |  |  |  |  | Send project update to internal WDCO K5M group
20 | 21 | 22 | 23 | 24 | 25 | 26
FF&E mock-up production, QC and packing
FF&E production
Fit-Out production |  |  |  |  | Send project update to client-facing group
⚑ Fit-out SHD V01 & material-package approval |  | Fit-out production, QC and packing
Send project update to internal WDCO K5M group
27 | 28 | 29 | 30
FF&E mock-up production, QC and packing
Fit-out production, QC and packing
FF&E production
Send project update to internal WDCO K5M group

## Oct 2026
K5M — OCTOBER 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  |  |  | 1 | 2 | 3
FF&E mock-up production, QC and packing
Fit-out production, QC and packing
FF&E production
Send project update to internal WDCO K5M group
4 | 5 | 6 | 7 | 8 | 9 | 10
FF&E mock-up production, QC and packing
Fit-out production, QC and packing
FF&E production | [5 empty] | Packing, dispatch, sea freight, customs, delivery
Send project update to client-facing group
Send project update to internal WDCO K5M group
11 | 12 | 13 | 14 | 15 | 16 | 17
FF&E mock-up production, QC and packing
Packing, dispatch, sea freight, customs, delivery
Fit-out production, QC and packing
Send project update to internal WDCO K5M group
18 | 19 | 20 | 21 | 22 | 23 | 24
Packing, dispatch, sea freight, customs, delivery
FF&E mock-up production, QC and packing
Send project update to client-facing group
Send project update to internal WDCO K5M group
25 | 26 | 27 | 28 | 29 | 30 | 31
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
⚑ Combined dispatch on next available sailing |  |  |  |  | Send project update to internal WDCO K5M group

## Nov 2026
K5M — NOVEMBER 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
1 | 2 | 3 | 4 | 5 | 6 | 7
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
Send project update to client-facing group
Send project update to internal WDCO K5M group
8 | 9 | 10 | 11 | 12 | 13 | 14
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
Send project update to internal WDCO K5M group
15 | 16 | 17 | 18 | 19 | 20 | 21
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
⚑ Internal working deadline |  |  |  |  | Send project update to client-facing group
Send project update to internal WDCO K5M group
22 | 23 | 24 | 25 | 26 | 27 | 28
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
Send project update to internal WDCO K5M group
29 | 30
Fit-Out and FF&E installation
Sea freight to Casablanca |  |  |  |  | Fit-out installation
Customs, port release, delivery to site
Send project update to client-facing group
Send project update to internal WDCO K5M group

## Dec 2026
K5M — DECEMBER 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  | 1 | 2 | 3 | 4 | 5
Fit-Out and FF&E installation
Sea freight to Casablanca |  |  |  |  | Fit-out installation
Customs, port release, delivery to site
Send project update to client-facing group
Send project update to internal WDCO K5M group
6 | 7 | 8 | 9 | 10 | 11 | 12
Fit-out installation
Fit-Out and FF&E installation
Customs, port release, delivery to site |  |  |  |  | Send project update to internal WDCO K5M group
13 | 14 | 15 | 16 | 17 | 18 | 19
Fit-out installation | [5 empty] | FF&E installation
Fit-Out and FF&E installation | ⚑ Ready for site inspection | ⚑ Hard deadline (as communicated to supplier) |  |  | Send project update to client-facing group
Send project update to internal WDCO K5M group
20 | 21 | 22 | 23 | 24 | 25 | 26
FF&E installation |  |  |  |  | Send project update to internal WDCO K5M group
⚑ Complete T1B1 mock-up ready for inspection
27 | 28 | 29 | 30 | 31

## Hard Milestones
K5M — HARD MILESTONES
Client |  |  |  |  | Supplier |  |  |  | WDCO Internal PM |  |  |  |  | Deadline (red border)
v2 draft — mini-month overview, Jul-Dec 2026. Deadline days highlighted directly on the mini calendars; matching list on the right. Not yet confirmed as the final definition of "deadline".
JULY 2026 | [6 empty] | AUGUST 2026 | [7 empty] | Date | Category | Deadline | Notes
S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | 15 Jul 2026 | Client | Project kick-off | Milestone.
|  |  | 1 | 2 | 3 | 4 | [6 empty] | 1 |  | 22 Jul 2026 | Supplier | SHD V00 parallel review & feedback | 28 Jul is the hard feedback deadline.
5 | 6 | 7 | 8 | 9 | 10 | 11 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 27 Jul 2026 | Supplier | Material scope issued to Production Partner | Milestone.
12 | 13 | 14 | 15 | 16 | 17 | 18 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | 30 Jul 2026 | Client | Fit-out RFI closure | Milestone.
19 | 20 | 21 | 22 | 23 | 24 | 25 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |  | 08 Aug 2026 | Supplier | Dispatch/delivery Round 1 sample box to Dubai | Must reach WDCO Dubai by 10 Aug.
26 | 27 | 28 | 29 | 30 | 31 |  | 23 | 24 | 25 | 26 | 27 | 28 | 29 |  | 12 Aug 2026 | Supplier | Signed GFP SHD Version 02 | Required before production release.
[7 empty] | 30 | 31 | [6 empty] | 24 Aug 2026 | Client | G&B team availability resumes | Office unavailable 1-24 Aug.
[15 empty] | 03 Sep 2026 | Client | Signed FF&E SHD V02 & confirmed material package | Production starts only after this.
[15 empty] | 10 Sep 2026 | Supplier | Signed GFP Fit-Out SHD | Required before production starts.
[15 empty] | 16 Sep 2026 | Client | Fit-out SHD V01 & material-package approval | Final fit-out production-release gate.
SEPTEMBER 2026 | [6 empty] | OCTOBER 2026 | [7 empty] | 25 Oct 2026 | Client | Combined dispatch on next available sailing | Milestone.
S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | 15 Nov 2026 | WDCO Internal PM | Internal working deadline | Supplier's 15 Dec hard deadline is unconfirmed; treat 15 Nov as the real internal target.
|  | 1 | 2 | 3 | 4 | 5 |  |  |  |  | 1 | 2 | 3 |  | 14 Dec 2026 | Supplier | Ready for site inspection | All contracted installation complete.
6 | 7 | 8 | 9 | 10 | 11 | 12 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 15 Dec 2026 | Supplier | Hard deadline (as communicated to supplier) | Tentative, not yet confirmed.
13 | 14 | 15 | 16 | 17 | 18 | 19 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |  | 20 Dec 2026 | Client | Complete T1B1 mock-up ready for inspection | Indicative revised readiness date.
20 | 21 | 22 | 23 | 24 | 25 | 26 | 18 | 19 | 20 | 21 | 22 | 23 | 24
27 | 28 | 29 | 30 |  |  |  | 25 | 26 | 27 | 28 | 29 | 30 | 31
NOVEMBER 2026 | [6 empty] | DECEMBER 2026
S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  | 1 | 2 | 3 | 4 | 5
8 | 9 | 10 | 11 | 12 | 13 | 14 | 6 | 7 | 8 | 9 | 10 | 11 | 12
15 | 16 | 17 | 18 | 19 | 20 | 21 | 13 | 14 | 15 | 16 | 17 | 18 | 19
22 | 23 | 24 | 25 | 26 | 27 | 28 | 20 | 21 | 22 | 23 | 24 | 25 | 26
29 | 30 | [5 empty] | 27 | 28 | 29 | 30 | 31

## Project Development Log
K5M — PROJECT DEVELOPMENT LOG
Client | Supplier | WDCO Internal PM | Deadline (red border)
Free-running narrative log, fed by '#projectdevelopment' entries. Category and Umbrella Task are tagged at end-of-day during #totalcheck, not necessarily live. Evidence is a hyperlink to whatever source Shagun provides (email, document, etc.), for cross-checking later.
Date | Category | Umbrella Task | Update | Evidence
2026-07-29 | Client | COMM-C | Sent full Material Package email to G&B, covering both FFE and Fitout. | Link
2026-07-29 | WDCO Internal PM | WIPM | Project Calendar built (v1 + v2) — only aesthetic alignment left.
2026-07-29 | Client | RFI-C | Raised an RFI with the client regarding a high-resolution picture of GL-8. | Link
2026-07-29 | Client | FOSHD | Adil (architect) sent the DWG file of the entrance door. | Link
2026-07-29 | Client | WIPM | New lighting designer introduced; details to be updated in CONTACT_SHEET.md once confirmed.
2026-07-29 | WDCO Internal PM |  | Meeting with Claire held — MoM to follow tomorrow.
2026-07-29 | Client | FOSHD | Closed fit-out RFIs with assigned actions; informed the client, will branch out further via email. | Link