## 9th July
K5M - T1B1 MOCK-UP ¦ PROJECT PLAN
TARGET: Complete T1B1 mock-up fully installed and ready for inspection by November 2026
[7 empty] | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23
PROJECT ACTIVITIES | [6 empty] | 2026-07-15: Jul 2026; 2026-08-05: Aug 2026; 2026-09-02: Sept 2026; 2026-10-07: Oct 2026; 2026-11-04: Nov 2026; 2026-12-02: Dec 2026
Activity / Task | Responsibility | Start | Finish | Days | Day Basis | Notes / Required Action | 15 Jul | 22 Jul | 29 Jul | 05 Aug | 12 Aug | 19 Aug | 26 Aug | 02 Sep | 09 Sep | 16 Sep | 23 Sep | 30 Sep | 07 Oct | 14 Oct | 21 Oct | 28 Oct | 04 Nov | 11 Nov | 18 Nov | 25 Nov | 02 Dec | 09 Dec | 16 Dec | 23 Dec
PROJECT COMMENCEMENT
Project kick-off | Wood Couture / Project Team | 2026-07-15 | 2026-07-15 | 0 | Milestone | Kick-off completed. | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
First RFI and FF&E SHD Version 00 issue | Wood Couture | 2026-07-16 | 2026-07-22 | 7 | Calendar days | Issued within seven days of kick-off. | bar: Jul 2026 15 Jul to Jul 2026 22 Jul
FFE - RFI, SHDs AND MATERIAL PACKAGE APPROVALS
FF&E SHD V00 parallel review and feedback | Client Design Team / Wood Couture / WC Production | 2026-07-23 | 2026-07-29 | 5 | Working days | Parallel review following Version 00 issue. | bar: Jul 2026 22 Jul to Jul 2026 29 Jul
FF&E SHD Version 01 drafting | Wood Couture | 2026-07-30 | 2026-08-03 | 3 | Working days | Drafting after Version 00 feedback. | bar: Jul 2026 29 Jul
FF&E SHD Version 01 & Material Package Submission - parallel review and feedback | Client Design Team / Wood Couture / WC Production | 2026-08-04 | 2026-08-10 | 5 | Working days | One-week review loop. | bar: Jul 2026 29 Jul to Aug 2026 05 Aug
FF&E SHD Version 02 drafting | Wood Couture | 2026-08-11 | 2026-08-13 | 3 | Working days | Final drafting based on consolidated feedback. | bar: Aug 2026 05 Aug to Aug 2026 12 Aug
Signed FF&E SHD Version 02 and confirmed material package | Client Design Team | 2026-08-14 | 2026-08-19 | 4 | Working days | Production-release gate: signed drawing and confirmed material package. | bar: Aug 2026 12 Aug to Aug 2026 19 Aug
FIT-OUT DRAWINGS, SURVEY AND APPROVALS
Fit-out RFI closure | Client / Architect | 2026-07-30 | 2026-07-30 | 0 | Milestone | Fit-out clarifications closed before completing the drawing package. | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
Fit-out site survey | Wood Couture | 2026-07-22 | 2026-07-24 | 3 | Calendar days | The site survey needs be completed before Version 00 development. | bar: Jul 2026 22 Jul
Fit-out site-survey report | Wood Couture | 2026-07-23 | 2026-07-28 | 4 | Working days | Survey findings documented while Version 00 development progressed. | bar: Jul 2026 22 Jul
Fit-out SHD Version 00 and preliminary material package | Wood Couture / WC Production | 2026-07-23 | 2026-08-10 | 19 | Calendar days | Developed from the site survey and available architectural information. | bar: Jul 2026 22 Jul to Aug 2026 05 Aug
Fit-out SHD Version 00 review | Client Design Team | 2026-08-11 | 2026-08-17 | 5 | Working days | Design review and feedback loop | bar: Aug 2026 05 Aug to Aug 2026 12 Aug
Fit-out SHD Version 01 revisions | Wood Couture / WC Production | 2026-08-11 | 2026-08-19 | 7 | Working days | Survey information and parallel comments incorporated. | bar: Aug 2026 05 Aug to Aug 2026 19 Aug
Fit-out SHD Version 01 and material-package approval | Client Design Team | 2026-08-20 | 2026-08-25 | 4 | Working days | Final fit-out production-release gate. | bar: Aug 2026 19 Aug
WDCO PRODUCTION
FF&E mock-up production, QC and packing | WC Production | 2026-08-20 | 2026-10-03 | 45 | Calendar days | bar: Aug 2026 19 Aug to Sept 2026 30 Sep
Fit-out production, QC and packing | WC Production | 2026-08-26 | 2026-09-19 | 25 | Calendar days | bar: Aug 2026 26 Aug to Sept 2026 16 Sep
LOGISTICS
Combined dispatch on next available sailing | Wood Couture / Forwarder | 2026-10-04 | 2026-10-04 | 0 | Milestone | FF&E and fit-out packages dispatch together. | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
Sea freight to Casablanca | Forwarder | 2026-10-04 | 2026-11-12 | 40 | Calendar days | Sea-freight allowance | bar: Sept 2026 30 Sep to Nov 2026 11 Nov
Customs, port release and delivery to site | Importer / Forwarder | 2026-11-12 | 2026-11-16 | 5 | Milestone | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
ON-SITE INSTALLATION AND COMPLETION
Fit-out installation | WC Installation Team | 2026-11-16 | 2026-11-30 | 15 | Calendar days | Fit-out installation precedes FF&E installation. | bar: Nov 2026 11 Nov to Nov 2026 25 Nov
FF&E installation | WC Installation Team | 2026-11-28 | 2026-11-29 | 2 | Calendar days | Two-day FF&E installation after fit-out. | bar: Nov 2026 25 Nov
Complete T1B1 mock-up ready for inspection | All Parties | 2026-11-30 | 2026-11-30 |  | Milestone | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
PROGRAMME BASIS: The same task durations are used in Project Plan Versions 1 and 2. Blue cells show editable dates, durations and day basis. Milestones are shown as 0 days. | bar: Jul 2026 15 Jul to Dec 2026 23 Dec

## 21st July
K5M - T1B1 MOCK-UP ¦ PROJECT PLAN
INDICATIVE REVISED READINESS: 20 December 2026 ¦ Subject to the confirmations noted below
[7 empty] | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23
CHANGE LOG
15.07.2026 |  | G&B informed in the kick off meeting their office wont be operational from 1st August to 24th August.
17.07.2026 |  | Got confirmation on whitebox availbality for site survey will be 30th August and not immediate as before.
PROJECT ACTIVITIES | [6 empty] | 2026-07-15: Jul 2026; 2026-08-05: Aug 2026; 2026-09-02: Sept 2026; 2026-10-07: Oct 2026; 2026-11-04: Nov 2026; 2026-12-02: Dec 2026
Activity / Task | Responsibility | Start | Finish | Days | Day Basis | Notes / Required Action | 15 Jul | 22 Jul | 29 Jul | 05 Aug | 12 Aug | 19 Aug | 26 Aug | 02 Sep | 09 Sep | 16 Sep | 23 Sep | 30 Sep | 07 Oct | 14 Oct | 21 Oct | 28 Oct | 04 Nov | 11 Nov | 18 Nov | 25 Nov | 02 Dec | 09 Dec | 16 Dec | 23 Dec
PROJECT COMMENCEMENT
Project kick-off | Wood Couture / Project Team | 2026-07-15 | 2026-07-15 | 0 | Milestone | Kick-off completed. | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
First RFI and FF&E SHD Version 00 issue | Wood Couture | 2026-07-16 | 2026-07-22 | 7 | Calendar days | Issued within seven days of kick-off. | bar: Jul 2026 15 Jul to Jul 2026 22 Jul
DESIGN-TEAM INPUT AND FF&E APPROVALS
G&B Team availability | Client Design Team | 2026-08-24 | 2026-08-24 |  | Milestone | Formal review resumes after 24th August ( Team unavailable between 1–23 August). | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
FF&E SHD V00 parallel review and feedback | Client Design Team / Wood Couture / WC Production | 2026-07-23 | 2026-07-29 | 5 | Working days | Internal and WDCO Production feedback can progress in parallel. | bar: Jul 2026 22 Jul to Jul 2026 29 Jul
FF&E SHD Version 01 drafting | Wood Couture | 2026-07-30 | 2026-08-03 | 3 | Working days | Developed while G&B team review is unavailable. | bar: Jul 2026 29 Jul
FF&E SHD Version 01 & Material Package Submission - parallel review and feedback | Client Design Team / Wood Couture / WC Production | 2026-08-24 | 2026-08-28 | 5 | Working days | Formal parallel review resumes on 24 August. | bar: Aug 2026 19 Aug to Aug 2026 26 Aug
FF&E SHD Version 02 drafting | Wood Couture | 2026-08-31 | 2026-09-02 | 3 | Working days | Final drafting after Version 01 feedback. | bar: Aug 2026 26 Aug to Sept 2026 02 Sep
Signed FF&E SHD Version 02 and confirmed material package | Client Design Team | 2026-09-03 | 2026-09-08 | 4 | Working days | Production starts only after signed Version 02 and confirmed materials. | bar: Sept 2026 02 Sep
FIT-OUT DRAWINGS, SURVEY AND APPROVALS
Fit-out RFI closure | Client / Architect | 2026-07-30 | 2026-07-30 | 0 | Milestone | Required before completing the fit-out drawing package. Have changed the activity sequence to utilize time till white box availability | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
Fit-out site survey | Wood Couture | 2026-08-31 | 2026-08-31 | 1 | Calendar days | Survey planned once the white box is ready. | bar: Aug 2026 26 Aug
Fit-out site-survey report | Wood Couture | 2026-09-01 | 2026-09-04 | 4 | Working days | Three to four working days after the survey. | bar: Aug 2026 26 Aug to Sept 2026 02 Sep
Fit-out SHD Version 00 and preliminary material package | Wood Couture / WC Production | 2026-08-03 | 2026-08-21 | 19 | Calendar days | Developed from the available architectural drawings before the site survey. | bar: Jul 2026 29 Jul to Aug 2026 19 Aug
Fit-out SHD Version 00 review and agreement in principle | Client Design Team | 2026-08-24 | 2026-08-28 | 5 | Working days | Agreement in principle before survey-dependent Version 01. (Assumption approval is issued from Architect office in Morocco) | bar: Aug 2026 19 Aug to Aug 2026 26 Aug
Fit-out SHD Version 01 revisions | Wood Couture / WC Production | 2026-09-07 | 2026-09-15 | 7 | Working days | Site-survey findings and parallel feedback incorporated into Version 01. | bar: Sept 2026 02 Sep to Sept 2026 09 Sep
Fit-out SHD Version 01 and material-package approval | Client Design Team | 2026-09-16 | 2026-09-21 | 4 | Working days | Final fit-out production-release gate. | bar: Sept 2026 16 Sep
WDCO PRODUCTION
FF&E mock-up production, QC and packing | WC Production | 2026-09-09 | 2026-10-23 | 45 | Calendar days | bar: Sept 2026 09 Sep to Oct 2026 21 Oct
Fit-out production, QC and packing | WC Production | 2026-09-22 | 2026-10-16 | 25 | Calendar days | bar: Sept 2026 16 Sep to Oct 2026 14 Oct
LOGISTICS
Combined dispatch on next available sailing | Wood Couture / Forwarder | 2026-10-25 | 2026-10-25 | 0 | Milestone | Controlled by completion of both packages and the next available sailing. | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
Sea freight to Casablanca | Forwarder | 2026-10-25 | 2026-12-03 | 40 | Calendar days | Sea-freight allowance | bar: Oct 2026 21 Oct to Dec 2026 02 Dec
Customs, port release and delivery to site | Importer / Forwarder | 2026-12-03 | 2026-12-07 | 5 | Milestone | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
ON-SITE INSTALLATION AND COMPLETION
Fit-out installation | WC Installation Team | 2026-12-04 | 2026-12-18 | 15 | Calendar days | Fit-out installation precedes FF&E installation. | bar: Dec 2026 02 Dec to Dec 2026 16 Dec
FF&E installation | WC Installation Team | 2026-12-19 | 2026-12-20 | 2 | Calendar days | Two-day FF&E installation after fit-out. | bar: Dec 2026 16 Dec
Complete T1B1 mock-up ready for inspection | All Parties | 2026-12-20 | 2026-12-20 | 0 | Milestone | bar: Jul 2026 15 Jul to Dec 2026 23 Dec
INDICATIVE REVISED READINESS: 20 December 2026
OPEN CONFIRMATIONS
Site access |  | Please confirm whether the site will remain accessible for Wood Couture's fit-out survey on 31 August 2026, considering the site holiday period (Mawlid) shown from 25 August to 15 September 2026.