## Data
K5M — PROJECT CALENDAR — SOURCE DATA
Client |  | Supplier |  | WDCO Internal PM |  | Deadline (red border)
v2 — 29 July 2026. One-off activities above the recurring-rule rows at the bottom. Recurring tasks need only one row (Recurs/Weekday/Until filled in) — they expand automatically onto the month tabs, not as individual rows here.
Start | End | Category | Activity | Notes | Is Deadline | Recurs | Recurs Weekday | Recurs Until
2026-07-15 |  | Client | Project kick-off | Milestone. | Y
2026-07-15 |  | WDCO Internal PM | G&B office unavailable 1-24 Aug | Informed at kick-off meeting. | N
2026-07-16 | 2026-07-22 | Client | First RFI and FF&E SHD V00 issue | Issued within 7 days of kick-off. | N
2026-07-17 |  | WDCO Internal PM | White-box availability confirmed as 30 Aug | Was assumed immediate before. | N
2026-07-22 | 2026-07-28 | Supplier | SHD V00 parallel review & feedback | 28 Jul is the hard feedback deadline. | Y
2026-07-23 | 2026-07-29 | Client | FF&E SHD V00 parallel review & feedback |  | N
2026-07-27 |  | Supplier | Material scope issued to Production Partner | Milestone. | Y
2026-07-27 | 2026-08-07 | Supplier | Round 1 sample-box development | 12 calendar days. | N
2026-07-29 | 2026-08-04 | Supplier | SHD V01 drafting and issue |  | N
2026-07-30 | 2026-08-03 | Client | FF&E SHD V01 drafting | Developed while G&B review unavailable. | N
2026-07-30 |  | Client | Fit-out RFI closure | Milestone. | Y
2026-07-31 | 2026-08-20 | Supplier | Fit-Out SHD Version 00 | Prepared from available architectural info. | N
2026-08-03 | 2026-08-21 | Client | Fit-out SHD V00 & preliminary material package |  | N
2026-08-05 | 2026-08-11 | Supplier | SHD V01 parallel review & feedback | Only controlled final coordination follows. | N
2026-08-08 | 2026-08-10 | Supplier | Dispatch/delivery Round 1 sample box to Dubai | Must reach WDCO Dubai by 10 Aug. | Y
2026-08-11 | 2026-09-10 | Supplier | Feedback round & final approved material box | Close by 10 Sept. | N
2026-08-12 | 2026-09-10 | Supplier | Signed GFP SHD Version 02 | Required before production release. | Y
2026-08-24 |  | Client | G&B team availability resumes | Office unavailable 1-24 Aug. | Y
2026-08-24 | 2026-08-28 | Client | FF&E SHD V01 & Material Package review | Formal parallel review resumes 24 Aug. | N
2026-08-24 | 2026-08-28 | Client | Fit-out SHD V00 review & agreement in principle | Assumes approval from Architect office. | N
2026-08-25 | 2026-09-15 | WDCO Internal PM | Site holiday period (Mawlid) | Open confirmation: is site accessible for the 31 Aug survey despite this? | N
2026-08-31 | 2026-09-02 | Client | FF&E SHD V02 drafting | Final drafting after V01 feedback. | N
2026-08-31 |  | Client | Fit-out site survey | Planned once white box is ready. | N
2026-08-31 |  | Supplier | Site visit / measurement | Milestone. | N
2026-09-01 | 2026-09-04 | Client | Fit-out site-survey report | 3-4 working days after survey. | N
2026-09-01 | 2026-09-03 | Supplier | Site survey report | Issued by 3 Sept. | N
2026-09-03 | 2026-09-08 | Client | Signed FF&E SHD V02 & confirmed material package | Production starts only after this. | Y
2026-09-04 | 2026-09-10 | Supplier | Fit-Out SHD V01 incorporating survey |  | N
2026-09-07 | 2026-09-15 | Client | Fit-out SHD V01 revisions | Site-survey findings incorporated. | N
2026-09-09 | 2026-10-23 | Client | FF&E mock-up production, QC and packing |  | N
2026-09-10 | 2026-10-09 | Supplier | FF&E production | Begins only after signed GFP SHD. | N
2026-09-10 |  | Supplier | Signed GFP Fit-Out SHD | Required before production starts. | Y
2026-09-10 | 2026-09-24 | Supplier | Fit-Out production |  | N
2026-09-16 | 2026-09-21 | Client | Fit-out SHD V01 & material-package approval | Final fit-out production-release gate. | Y
2026-09-22 | 2026-10-16 | Client | Fit-out production, QC and packing |  | N
2026-10-10 | 2026-11-28 | Supplier | Packing, dispatch, sea freight, customs, delivery | Both packages together. | N
2026-10-25 |  | Client | Combined dispatch on next available sailing | Milestone. | Y
2026-10-25 | 2026-12-03 | Client | Sea freight to Casablanca |  | N
2026-11-15 |  | WDCO Internal PM | Internal working deadline | Supplier's 15 Dec hard deadline is unconfirmed; treat 15 Nov as the real internal target. | Y
2026-11-29 | 2026-12-13 | Supplier | Fit-Out and FF&E installation |  | N
2026-12-03 | 2026-12-07 | Client | Customs, port release, delivery to site |  | N
2026-12-04 | 2026-12-18 | Client | Fit-out installation | Precedes FF&E installation. | N
2026-12-14 |  | Supplier | Ready for site inspection | All contracted installation complete. | Y
2026-12-15 |  | Supplier | Hard deadline (as communicated to supplier) | Tentative, not yet confirmed. | Y
2026-12-19 | 2026-12-20 | Client | FF&E installation |  | N
2026-12-20 |  | Client | Complete T1B1 mock-up ready for inspection | Indicative revised readiness date. | Y
2026-07-31 |  | Client | Send project update to client-facing group | Recurring — biweekly, anchored 31 Jul 2026. | N | Biweekly | Friday | 2026-12-31
2026-07-31 |  | WDCO Internal PM | Send project update to internal WDCO K5M group | Recurring — weekly, anchored 31 Jul 2026. | N | Weekly | Friday | 2026-12-31
2026-08-06 |  | Client | RFI with lighting designer must be closed | Raised 30 Jul 2026. | Y
2026-08-03 |  | Client | BOQ scope gap meeting — all stakeholders | Agenda: stone arch/wardrobe/fitted sofa, suspended glass light over basin, hardware & bathroom fittings. | Y

## Jul 2026
K5M — JULY 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  |  | 1 | 2 | 3 | 4
5 | 6 | 7 | 8 | 9 | 10 | 11
12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  | ⚑ Project kick-off | First RFI and FF&E SHD V00 issue
|  |  | G&B office unavailable 1-24 Aug |  | White-box availability confirmed as 30 Aug
19 | 20 | 21 | 22 | 23 | 24 | 25
First RFI and FF&E SHD V00 issue |  |  |  | FF&E SHD V00 parallel review & feedback
⚑ SHD V00 parallel review & feedback
26 | 27 | 28 | 29 | 30 | 31
FF&E SHD V00 parallel review & feedback |  |  |  | FF&E SHD V01 drafting
⚑ SHD V00 parallel review & feedback |  |  | SHD V01 drafting and issue
Round 1 sample-box development
| ⚑ Material scope issued to Production Partner |  |  | ⚑ Fit-out RFI closure | Fit-Out SHD Version 00
Send project update to client-facing group
Send project update to internal WDCO K5M group

## Aug 2026
K5M — AUGUST 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
1
FF&E SHD V00 parallel review & feedback |  |  |  | FF&E SHD V01 drafting
⚑ SHD V00 parallel review & feedback |  |  | SHD V01 drafting and issue
Round 1 sample-box development
| ⚑ Material scope issued to Production Partner |  |  | ⚑ Fit-out RFI closure | Fit-Out SHD Version 00
Send project update to client-facing group
Send project update to internal WDCO K5M group
2 | 3 | 4 | 5 | 6 | 7 | 8
Fit-Out SHD Version 00
Round 1 sample-box development | [5 empty] | ⚑ Dispatch/delivery Round 1 sample box to Dubai
SHD V01 drafting and issue |  |  | SHD V01 parallel review & feedback
FF&E SHD V01 drafting |  |  |  | ⚑ RFI with lighting designer due | Send project update to internal WDCO K5M group
Fit-out SHD V00 & preliminary material package
⚑ BOQ scope gap meeting
9 | 10 | 11 | 12 | 13 | 14 | 15
Fit-out SHD V00 & preliminary material package
Fit-Out SHD Version 00
SHD V01 parallel review & feedback |  |  | ⚑ Signed GFP SHD Version 02
⚑ Dispatch/delivery Round 1 sample box to Dubai |  | Feedback round & final approved material box
Send project update to client-facing group
Send project update to internal WDCO K5M group
16 | 17 | 18 | 19 | 20 | 21 | 22
Feedback round & final approved material box
⚑ Signed GFP SHD Version 02
Fit-out SHD V00 & preliminary material package
Fit-Out SHD Version 00 |  |  |  |  | Send project update to internal WDCO K5M group
23 | 24 | 25 | 26 | 27 | 28 | 29
Feedback round & final approved material box
⚑ Signed GFP SHD Version 02
FF&E SHD V01 & Material Package review
Fit-out SHD V00 review & agreement in principle
| ⚑ G&B team availability resumes | Site holiday period (Mawlid)
Send project update to client-facing group / +1 more (see Data tab)
30 | 31
Feedback round & final approved material box
⚑ Signed GFP SHD Version 02
Site holiday period (Mawlid)
| FF&E SHD V02 drafting |  |  | ⚑ Signed FF&E SHD V02 & confirmed material package
| Fit-out site survey | Fit-out site-survey report
| Site visit / measurement | Site survey report |  |  | Fit-Out SHD V01 incorporating survey / +1 more (see Data tab)

## Sep 2026
K5M — SEPTEMBER 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  | 1 | 2 | 3 | 4 | 5
Feedback round & final approved material box
⚑ Signed GFP SHD Version 02
Site holiday period (Mawlid)
| FF&E SHD V02 drafting |  |  | ⚑ Signed FF&E SHD V02 & confirmed material package
| Fit-out site survey | Fit-out site-survey report
| Site visit / measurement | Site survey report |  |  | Fit-Out SHD V01 incorporating survey / +1 more (see Data tab)
6 | 7 | 8 | 9 | 10 | 11 | 12
Site holiday period (Mawlid)
Feedback round & final approved material box |  |  |  |  | Send project update to client-facing group
⚑ Signed GFP SHD Version 02 |  |  |  |  | Send project update to internal WDCO K5M group
Fit-Out SHD V01 incorporating survey
⚑ Signed FF&E SHD V02 & confirmed material package |  |  | FF&E mock-up production, QC and packing
Fit-out SHD V01 revisions
13 | 14 | 15 | 16 | 17 | 18 | 19
FF&E mock-up production, QC and packing
FF&E production
Fit-Out production
Fit-out SHD V01 revisions |  |  | ⚑ Fit-out SHD V01 & material-package approval
Site holiday period (Mawlid) |  |  |  |  | Send project update to internal WDCO K5M group
20 | 21 | 22 | 23 | 24 | 25 | 26
FF&E mock-up production, QC and packing
FF&E production
Fit-Out production |  |  |  |  | Send project update to client-facing group
⚑ Fit-out SHD V01 & material-package approval |  | Fit-out production, QC and packing
Send project update to internal WDCO K5M group
27 | 28 | 29 | 30
FF&E mock-up production, QC and packing
Fit-out production, QC and packing
FF&E production
Send project update to internal WDCO K5M group

## Oct 2026
K5M — OCTOBER 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  |  |  | 1 | 2 | 3
FF&E mock-up production, QC and packing
Fit-out production, QC and packing
FF&E production
Send project update to internal WDCO K5M group
4 | 5 | 6 | 7 | 8 | 9 | 10
FF&E mock-up production, QC and packing
Fit-out production, QC and packing
FF&E production | [5 empty] | Packing, dispatch, sea freight, customs, delivery
Send project update to client-facing group
Send project update to internal WDCO K5M group
11 | 12 | 13 | 14 | 15 | 16 | 17
FF&E mock-up production, QC and packing
Packing, dispatch, sea freight, customs, delivery
Fit-out production, QC and packing
Send project update to internal WDCO K5M group
18 | 19 | 20 | 21 | 22 | 23 | 24
Packing, dispatch, sea freight, customs, delivery
FF&E mock-up production, QC and packing
Send project update to client-facing group
Send project update to internal WDCO K5M group
25 | 26 | 27 | 28 | 29 | 30 | 31
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
⚑ Combined dispatch on next available sailing |  |  |  |  | Send project update to internal WDCO K5M group

## Nov 2026
K5M — NOVEMBER 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
1 | 2 | 3 | 4 | 5 | 6 | 7
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
Send project update to client-facing group
Send project update to internal WDCO K5M group
8 | 9 | 10 | 11 | 12 | 13 | 14
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
Send project update to internal WDCO K5M group
15 | 16 | 17 | 18 | 19 | 20 | 21
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
⚑ Internal working deadline |  |  |  |  | Send project update to client-facing group
Send project update to internal WDCO K5M group
22 | 23 | 24 | 25 | 26 | 27 | 28
Sea freight to Casablanca
Packing, dispatch, sea freight, customs, delivery
Send project update to internal WDCO K5M group
29 | 30
Fit-Out and FF&E installation
Sea freight to Casablanca |  |  |  |  | Fit-out installation
Customs, port release, delivery to site
Send project update to client-facing group
Send project update to internal WDCO K5M group

## Dec 2026
K5M — DECEMBER 2026
Client | Supplier | WDCO Internal PM | Deadline (red border)
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  | 1 | 2 | 3 | 4 | 5
Fit-Out and FF&E installation
Sea freight to Casablanca |  |  |  |  | Fit-out installation
Customs, port release, delivery to site
Send project update to client-facing group
Send project update to internal WDCO K5M group
6 | 7 | 8 | 9 | 10 | 11 | 12
Fit-out installation
Fit-Out and FF&E installation
Customs, port release, delivery to site |  |  |  |  | Send project update to internal WDCO K5M group
13 | 14 | 15 | 16 | 17 | 18 | 19
Fit-out installation | [5 empty] | FF&E installation
Fit-Out and FF&E installation | ⚑ Ready for site inspection | ⚑ Hard deadline (as communicated to supplier) |  |  | Send project update to client-facing group
Send project update to internal WDCO K5M group
20 | 21 | 22 | 23 | 24 | 25 | 26
FF&E installation |  |  |  |  | Send project update to internal WDCO K5M group
⚑ Complete T1B1 mock-up ready for inspection
27 | 28 | 29 | 30 | 31

## Hard Milestones
K5M — HARD MILESTONES
Client |  |  |  |  | Supplier |  |  |  | WDCO Internal PM |  |  |  |  | Deadline (red border)
v2 draft — mini-month overview, Jul-Dec 2026. Deadline days highlighted directly on the mini calendars; matching list on the right. Not yet confirmed as the final definition of "deadline".
JULY 2026 | [6 empty] | AUGUST 2026 | [7 empty] | Date | Category | Deadline | Notes
S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | 15 Jul 2026 | Client | Project kick-off | Milestone.
|  |  | 1 | 2 | 3 | 4 | [6 empty] | 1 |  | 22 Jul 2026 | Supplier | SHD V00 parallel review & feedback | 28 Jul is the hard feedback deadline.
5 | 6 | 7 | 8 | 9 | 10 | 11 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 27 Jul 2026 | Supplier | Material scope issued to Production Partner | Milestone.
12 | 13 | 14 | 15 | 16 | 17 | 18 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | 30 Jul 2026 | Client | Fit-out RFI closure | Milestone.
19 | 20 | 21 | 22 | 23 | 24 | 25 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |  | 08 Aug 2026 | Supplier | Dispatch/delivery Round 1 sample box to Dubai | Must reach WDCO Dubai by 10 Aug. (#50) Shagun has put H&T on notice: management escalation + Plan-B sourcing if this slips.
26 | 27 | 28 | 29 | 30 | 31 |  | 23 | 24 | 25 | 26 | 27 | 28 | 29 |  | 12 Aug 2026 | Supplier | Signed GFP SHD Version 02 | Required before production release.
[7 empty] | 30 | 31 | [6 empty] | 24 Aug 2026 | Client | G&B team availability resumes | Office unavailable 1-24 Aug.
[15 empty] | 03 Sep 2026 | Client | Signed FF&E SHD V02 & confirmed material package | Production starts only after this.
[15 empty] | 10 Sep 2026 | Supplier | Signed GFP Fit-Out SHD | Required before production starts.
[15 empty] | 16 Sep 2026 | Client | Fit-out SHD V01 & material-package approval | Final fit-out production-release gate.
SEPTEMBER 2026 | [6 empty] | OCTOBER 2026 | [7 empty] | 25 Oct 2026 | Client | Combined dispatch on next available sailing | Milestone.
S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | 15 Nov 2026 | WDCO Internal PM | Internal working deadline | Supplier's 15 Dec hard deadline is unconfirmed; treat 15 Nov as the real internal target.
|  | 1 | 2 | 3 | 4 | 5 |  |  |  |  | 1 | 2 | 3 |  | 14 Dec 2026 | Supplier | Ready for site inspection | All contracted installation complete.
6 | 7 | 8 | 9 | 10 | 11 | 12 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 15 Dec 2026 | Supplier | Hard deadline (as communicated to supplier) | Tentative, not yet confirmed.
13 | 14 | 15 | 16 | 17 | 18 | 19 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |  | 20 Dec 2026 | Client | Complete T1B1 mock-up ready for inspection | Indicative revised readiness date — later than the actual contractual milestone (30 Nov, see row above). (#49) Needs reconciling with Filippo/Claire.
20 | 21 | 22 | 23 | 24 | 25 | 26 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  | 06 Aug 2026 | Client | RFI with lighting designer must be closed | Raised 30 Jul 2026.
27 | 28 | 29 | 30 |  |  |  | 25 | 26 | 27 | 28 | 29 | 30 | 31 |  | 03 Aug 2026 | Client | BOQ scope gap meeting — all stakeholders | Agenda: see meetings/260803_K5M_Meeting_BOQ_Scope_Gap.
[15 empty] | 30 Nov 2026 | Client | T1B1 mock-up contractual deadline | (#49) Hard contractual milestone per the original award letter, cited by Filippo Sona 6 Aug — fully completed, installed, ready for review/approval. Predates and is earlier than the 20 Dec indicative date below.
[15 empty] | 10 Oct 2026 | WDCO Internal PM | Container shipment hard deadline | (#40) Confirmed 7 Aug with Maria Al Balushi — target departure window 5-10 Oct, ~30 pieces for one room. Full weight/size estimate still due end of August.
[15 empty] | 16 Aug 2026 | Supplier | K5M factory materials completion (flagged risk) | (#56) Khamille's high-importance flag, 7 Aug — previously understood to be already in preparation. Coincides with Material Package Fitout's own 10-day sample turnaround target.
NOVEMBER 2026 | [6 empty] | DECEMBER 2026
S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  | 1 | 2 | 3 | 4 | 5
8 | 9 | 10 | 11 | 12 | 13 | 14 | 6 | 7 | 8 | 9 | 10 | 11 | 12
15 | 16 | 17 | 18 | 19 | 20 | 21 | 13 | 14 | 15 | 16 | 17 | 18 | 19
22 | 23 | 24 | 25 | 26 | 27 | 28 | 20 | 21 | 22 | 23 | 24 | 25 | 26
29 | 30 | [5 empty] | 27 | 28 | 29 | 30 | 31

## Project Development Log
K5M — PROJECT DEVELOPMENT LOG
Client | Supplier | WDCO Internal PM | Deadline (red border)
Free-running narrative log, fed by '#projectdevelopment' entries. Category and Umbrella Task are tagged at end-of-day during #totalcheck, not necessarily live. Evidence is a hyperlink to whatever source Shagun provides (email, document, etc.), for cross-checking later.
Date | Category | Umbrella Task | Update | Evidence
2026-07-29 | Client | Communication Management - Client | Sent full Material Package email to G&B, covering both FFE and Fitout. | Link
2026-07-29 | WDCO Internal PM | WDCO Internal Project Management | Project Calendar built (v1 + v2) — only aesthetic alignment left.
2026-07-29 | Client | RFI - Client | Raised an RFI with the client regarding a high-resolution picture of GL-8. | Link
2026-07-29 | Client | Fitout SHD | Adil (architect) sent the DWG file of the entrance door. | Link
2026-07-29 | Client | WDCO Internal Project Management | New lighting designer introduced; details to be updated in CONTACT_SHEET.md once confirmed.
2026-07-29 | WDCO Internal PM |  | Meeting with Claire held — MoM to follow tomorrow.
2026-07-29 | Client | Fitout SHD | Closed fit-out RFIs with assigned actions; informed the client, will branch out further via email. | Link
2026-07-30 | Client | Communication Management - Client | Sent introduction email to the new lighting designer.
2026-07-30 | Client | RFI - Client | Raised a new RFI with the lighting designer — must close by 6 Aug 2026.
2026-07-30 | Client | RFI - Client | Sent lighting designer (Gisela Steiger) a full status update on both scopes, referencing the still-open FF&E lighting RFI directly. | Link
2026-07-30 | Client | Project Scope | BOQ scope gap meeting confirmed for Monday 3 Aug — agenda: stone arch over wardrobe/fitted sofa, suspended glass light over basin, hardware & bathroom fittings.
2026-07-30 | Supplier | Material Package FFE | H&T followed up on the Material Package — confirmed today's review meeting at 10am to go through it together.
2026-07-30 | Client | Material Package Fitout | Valentine (design team) emailed confirming she's clear on the material package and asked for sample photos if possible. Will try to resolve this in today's H&T meeting; if not, will reply to her directly by 1pm today.
2026-07-30 | WDCO Internal PM | WDCO Internal Project Management | Started work on the Google SketchUp model for the project briefing.
2026-07-30 | WDCO Internal PM | Project Scope | Drafted a basic agenda for the BOQ scope gap meeting (Monday, 3 Aug) — alongside the formal agenda doc already prepared and stored in the project management folder.
2026-07-30 | Supplier | Fitout SHD | Sent Ariel all details for the fit-out drawings; Claire has asked to pause this, as a new team joinee starts Monday (3 Aug) — will assess whether he can take this on before deciding who owns the work.
2026-07-31 | Client | Material Package FFE | Sent Valentine (design team) a request for stone reference images for three FFE stones (Calacatta Oro, Taj Mahal, Alabaster) — attached internet-sourced reference images based on the names she provided, purely to align on general visual direction before sample development. | Link
2026-08-03 | WDCO Internal PM | Project Scope | BOQ gap meeting held. Decided: Resti's stone arch calculation to be documented clearly and incorporated into the existing scope-gap findings.
2026-08-03 | WDCO Internal PM | Communication Management - Internal | Decided to send a consolidated BOQ-changes email (the gap, the difference) to Filippo Sona (WDCO co-founder/main partner) to handle from there.
2026-08-03 | WDCO Internal PM | Logistics | Decided to email Maria (WDCO logistics) for container requirements so booking can proceed right away.
2026-08-03 | WDCO Internal PM | Project Scope | Decided to build a new Fitout Scope document — fully defined, with a "Doubts" section for removable/uncertain items. Resolves the long-pending Fitout base-scope file (Hard Rule 14).
2026-08-03 | Supplier | Fitout SHD | Decided to schedule a fitout scope meeting with H&T ASAP.
2026-08-03 | Supplier | Fitout SHD | Ariel to confirm which fitout drawings are shareable — deadline 7 Aug.
2026-08-03 | WDCO Internal PM | Site Survey Planning | Site visit timing remains under ambiguity; white-box photos and a post-site-survey deliverable required regardless.
2026-08-03 | WDCO Internal PM | Compliance Collection | Decided to compile all compliance documents received into a single consolidated record.
2026-08-04 | Client | Compliance Collection | Compliance documents request sent to Abdellatif Menbar (per Claire's direction); targeting close by 10 Aug.
2026-08-04 | Client | Fitout SHD | Sent Abdellatif Menbar the substructure requirements per Claire's direction; further discussion ongoing via email with the client team.
2026-08-04 | Client | Material Package FFE | Met with Khamille on sample development — agreed swatch quantities per material (Fitout: 5 Stone/3 Wood/4 Metal/4 Glass/3 Fabric/1 Seating; FFE: 2 Wood/5 Metal/2 Glass/3 Stone/10 Fabric) and swatch sizes (Fabric/Wood/Glass 14x10cm, Metal 10x7cm), plus a wood-swatch construction spec (real wood + associated veneer). Already shared with H&T. Presentation concept for the swatch box still to be developed.
2026-08-05 | WDCO Internal PM | FFE SHD | Internal FFE Shop Drawing (SHD01) review meeting held, 10:30am. MOM to follow.
2026-08-06 | WDCO Internal PM | Project Scope | Resti completed the stone arch BOQ gap calculation requested — write-up still to follow.

## Task Tracker
| 1 | Important and urgent
| 2 | Urgent but not important
| 3 | Important but not urgent
| 4 | Neither — just needs a place to live
Task Number | Date Raised | Task | Umbrella Task | Priority | Type of Task | Dependent On 1 | Dependent On 2 | Status | Due/Target Date | Note | Logged on Calendar?
1 | 2026-07-29 | Discuss with Claire — Material Package packaging (Claire vs Khamille) | Material Package FFE | 3 | Meeting physical | Claire |  | Done |  | Resolved via 29 Jul MoM.
2 | 2026-07-29 | Follow up with Khamille on sample presentation format & timeline | Material Package FFE | 1 | Follow up call | Khamille |  | To Do |  | Reinforced in 4 Aug meeting with Claire — align presentation/delivery method with internal guidelines, then use Khamille's guidance to prepare a complete sample presentation for H&T.
3 | 2026-07-29 | Discuss with Claire — fit-out substructure requirement approach | Fitout SHD | 2 | Meeting physical |  |  | Done |  | Resolved in 4 Aug meeting with Claire — agreed to ask Adil's site team to confirm what substructure work/info already exists, then start H&T communication (see row 4 and new row below).
4 |  | Send K5M "The Client" substrcture requirements for the fitout | RFI - Client | 1 |  | H&T |  | In Progress | 2026-08-05 | Due date corrected 31 Jul (was 05/09/2026, a month off) — matches the 5 Aug Calendar milestone and the urgency flagged in this week's risk-mitigation note: implementation cannot start until this is sent. Sent per Claire's 4 Aug direction; further discussion ongoing with Abdellatif Menbar via email — awaiting outcome (per 6 Aug update).
5 |  | Get Fitout Specification Drawings ready for supplier review / talk to Ariel about scaling and improving the fit-out drawing | Fitout SHD | 1 | Follow up email | Ariel |  | Stale |  | Sent Ariel all details. Claire has asked to pause — new team joinee starts Monday (3 Aug); will assess if he can take this on before deciding who owns the work. Superseded by S.No.31 ("Proceed with Ariel for required fit-out drawing updates; copy Resti") — same topic, decided at the 4 Aug meeting with Claire. Marked Stale + hidden by Woody, 6 Aug.
6 | 2026-07-29 | Build project contact sheet (security log) | Communication Management - Internal | 1 | Documentation |  |  | Done
7 | 2026-07-29 | Close the BOQ gap problem / Fit-out scope | Project Scope | 1 | Meeting physical |  |  | In Progress | 2026-08-03 | Stakeholder meeting scheduled Monday per 29 Jul MoM; no scope additions until then. Agenda topics confirmed 30 Jul: stone arch over wardrobe and fitted sofa, suspended glass light over the basin, fittings — hardware & bathroom. See meetings/260803_K5M_Meeting_BOQ_Scope_Gap/pre-meeting/agenda.md.
8 | 2026-07-29 | Fix a meeting with H&T — Material Package briefing | Material Package FFE | 2 | Meeting online |  |  | Done | 30th July | Meeting set at 10 am
9 | 29th july | Make an agenda for the HT material package review meeting. | Communication Management - Production Partner | 2 | Documentation |  |  | Stale | 29th july | Superseded — H&T Material Package review meeting already happened (30 Jul, 10am). Marked Stale + hidden by Woody during #totalcheck.
10 | 2026-07-29 | Form a central RFI tracking/management system within git | RFI - Internal | 3 | Documentation |  |  | To Do |  | Merged with former row 22 (duplicate ask) on 30 Jul per Shagun.
11 | 2026-07-30 | Brief H&T on fit-out scope and drawings + consolidated info request (substructure, sample drawings, technical data sheets) | Fitout SHD | 1 | Send an email |  |  | To Do | 2026-07-30 | Per 29 Jul MoM: one consolidated email, not sequential individual requests. Reinforced in 4 Aug meeting with Claire — start H&T comms on fit-out scope ASAP, share available info once site team responds, request any additional H&T needs immediately.
12 | 2026-07-30 | Finish the AI-created COC and shift to OneDrive to maintain from there | COC Management | 2 | Documentation |  |  | In Progress |  | Decided 3 Aug: full rebuild from scratch, once underlying data is fully verified/clean, rather than patching the 28 July v1. Freeze panes removed, Data tab rebuilt from canonical scope, and Hard Material partially updated as interim steps — but the ground-up rebuild is still the plan. Update 6 Aug: the rebuild is visibly underway — Shagun's own new build, 260804_K5M_Internal Central COC.xlsx (Desktop, not yet in git), has 5 sheets (FFE_Main Data Sheet, Change Log, FFE_Fabrics, FFE_Hard Material, Shop Drawing Tracker) with real content populated, not just structure. Worth committing to git once she's ready.
13 | 2026-07-30 | Finish formatting the Project Calendar and Task Tracker, and move both to OneDrive to maintain from there | WDCO Internal Project Management | 1 | Documentation |  |  | In Progress | 2026-07-30 | Merged with former row 24 (duplicate ask) on 30 Jul per Shagun. Aesthetic alignment pass by Shagun, then final push to OneDrive.
14 | 2026-07-30 | Collate feedback on FFE SHD00 to start work on SHD01 | FFE SHD | 2 | Documentation |  |  | Done |  | Done — all 17 FFE items with a WDCO code now have SHD00 feedback collated (63 remarks total across Client/Internal/Factory review) in Shagun's new Central COC build (260804_K5M_Internal Central COC.xlsx, Desktop). All still marked unresolved (Value=False); 44 already have an Action/Action Owner noted.
15 | 2026-07-30 | Fitout Fabrics — banquette fabric sheet — check with suppliers for samples | Material Package Fitout | 3 | Follow up email |  |  | In Progress |  | Per 31 Jul H&T meeting — Fit-out fabrics partially researched online, findings updated in the Excel sheet and fabric folder shared.
16 | 2026-07-30 | Create a Google SketchUp model for the project briefing | WDCO Internal Project Management | 1 | Arranging |  |  | In Progress | 2026-08-02 | Hoped for before Monday's meeting — Type of Task guessed, doesn't cleanly fit the 7 categories.
17 | 2026-07-30 | Add fitted-sofa client sample request to fabrication schedule and arrange sample | Material Package Fitout | 2 | Arranging |  |  | To Do |  | Per 29 Jul MoM.
18 | 2026-07-30 | Send WDCO project information to the new lighting designer | Communication Management - Client | 1 | Send an email |  |  | Done | 2026-07-30 | Introduction email sent 30 Jul. Still need the designer's actual name/email for CONTACT_SHEET.md.
19 | 2026-07-30 | Follow up with Victoire on glass sample GL-3A for better specification clarity | Material Package FFE | 3 | Follow up email |  |  | To Do |  | Per 29 Jul MoM.
20 | 2026-07-30 | Raise an RFI with the lighting designer | RFI - Client | 1 | Send an email |  |  | In Progress | 2026-08-06 | Email sent 30 Jul referencing the existing FF&E lighting RFI (Sheet 3, 'Lighting / Lighting Equipment Only RFI') — requested equipment details/compliance clarifications from Gisela. Recipient confirmed as the same Gisela Steiger already in CONTACT_SHEET.md, not a new contact. Awaiting her reply; must close by 6 Aug.
21 | 2026-07-30 | Follow up with Gisela — structured Fit-out RFI list and workflow | RFI - Client | 2 | Send an email |  |  | To Do | 2026-08-06 | Committed to this in the 30 Jul status email — 'by next week I should be able to share a clearer RFI list and workflow.'
22 | 2026-07-30 | Create a central RFI tracking system within git | RFI - Internal | 3 | Documentation |  |  | Stale |  | Merged into row 10 (duplicate) — marked Stale + hidden by Woody, 30 Jul.
23 | 2026-07-30 | Prepare agenda for BOQ scope gap meeting (Monday, 3 Aug) | Project Scope | 1 | Documentation |  |  | Done | 2026-07-30 | Agenda covers: stone arch over wardrobe/fitted sofa, suspended glass light over basin, hardware & bathroom fittings. Stored at meetings/260803_K5M_Meeting_BOQ_Scope_Gap/pre-meeting/agenda.md.
24 | 2026-07-30 | Finish formatting the Project Calendar and Task Tracker to shift both to OneDrive | WDCO Internal Project Management | 1 | Documentation |  |  | Stale | 2026-07-30 | Merged into row 13 (duplicate) — marked Stale + hidden by Woody, 30 Jul.
25 | 2026-07-30 | Reply to Valentine (design team) with material package sample photos, if not resolved in today's H&T meeting | Material Package Fitout | 2 | Send an email | H&T |  | To Do | 2026-07-30 | Contingent on today's 10am H&T Material Package review — reply directly to Valentine by 1pm today if not addressed there.
26 | 2026-07-30 | Decide redaction scope for real client/Production Partner names found in README.md, PROJECT_BRIEFING.md, SESSION_START.md, and DAILY_LOG.md (main branch) | WDCO Internal Project Management | 3 | Documentation |  |  | To Do |  | Flagged while building HARD_RULES.md — Shagun asked to hold off deciding scope (fix living docs only vs. also rewrite DAILY_LOG history vs. keep Wood Couture as-is). Revisit when ready.
27 | 2026-07-31 | Align all product codes across trackers (Material Package, COC Master Scope, client-facing documents) — especially client-facing product codes | COC Management | 1 | Documentation |  |  | In Progress |  | FFE scope codes now aligned (CH→CHA fixed 31 Jul in the canonical Master SKU List). Material Package’s own CHA-RT-01 error still unfixed there (Shagun deferred that edit). Fitout scope not yet confirmed — expected next week; recheck fitout codes once that lands.
28 | 2026-07-31 | Decide and inform Woody which project scope file(s) will be the base/authoritative source for all documents going forward | COC Management | 1 | Documentation |  |  | In Progress |  | FFE resolved 31 Jul — holy grail file confirmed: 260724_WDCOK5M_FFE_Master SKU List.xlsx (OneDrive, 00_SHARED/Project Scope). Now added to HARD_RULES.md. Fitout base scope file still pending — Shagun expects to confirm next week.
29 | 2026-07-31 | File H&T Meeting Minutes (MOM, 31 Jul — material package development) into the repo meeting folder | Communication Management - Production Partner | 2 | Documentation |  |  | Done | 2026-07-31 | Filed at meetings/260731_K5M_Meeting_H&T_Material_Package/minutes/. Not a duplicate of the #projectdevelopment Dev Log entries — those capture the narrative, this is the source document.
30 | 2026-08-04 | Ask H&T (China team) to begin developing first metal-sample finishes based on client reference images | Material Package FFE | 1 | Send an email | H&T |  | To Do |  | Per 4 Aug meeting with Claire: Paris design team clarified 3 coating finishes look similar but are different codes based on metal nature — doesn't align with VE. Agreed to proceed via H&T China team using client visual references rather than resolving the code discrepancy first.
31 | 2026-08-04 | Proceed with Ariel for required fit-out drawing updates; copy Resti | Fitout SHD | 1 | Send an email | Ariel | Resti | To Do |  | Per 4 Aug meeting with Claire — fit-out drawings must be updated before scope can float further. Resti (Head of Engineering, joined this week) copied to stay informed.
32 | 2026-08-04 | Request compliance sheets/certificates from Abdellatif Menbar (client) — hardware, bathroom fittings, electrical, stone anti-slip certification, foam, and any other regulated/specified materials | Compliance Collection | 1 | Send an email | Abdellatif Menbar |  | In Progress | 2026-08-10 | Per 4 Aug meeting with Claire. Share the Hyatt reference sheet found online; confirm whether any additional documents/formats are required. Target close 10 Aug (per 3 Aug BOQ gap meeting decision).
33 | 2026-08-04 | Ask Resti to recheck stone arch measurements/quantities; communicate scope gaps and changes since kick-off transparently to stakeholders | Project Scope | 1 | Documentation | Resti |  | Done |  | Per 4 Aug meeting with Claire — directly overlaps with the stone arch BOQ scope gap study already done and saved at meetings/260803_K5M_Meeting_BOQ_Scope_Gap/post-meeting/Fit-out BOQ Scope Gap/stone_arch_findings.md. Resti's recheck should reference that file. Resti completed the calculation (per 6 Aug update) — being incorporated into a clear write-up, see new row below.
34 | 2026-08-04 | Ask Adil's site team to confirm what substructure work/information has already been prepared | Fitout SHD | 1 | Send an email | Adil |  | To Do |  | Per 4 Aug meeting with Claire — substructure info is critical for fit-out drawings, BOQ, supplier scope, and sample development. Share available details with H&T once site team's input received (see row 11).
35 | 2026-08-04 | Plan the 31 Aug–1 Sep site visit — start comms with H&T on dates, prepare/circulate agenda (objectives, attendees, sample review, site activities, deliverables, responsibilities, timings); ask Abdellatif Menbar/Adil for site-access permits, accommodation, and site location/Maps link | Site Survey Planning | 1 | Documentation | H&T |  | In Progress |  | Per 4 Aug meeting with Claire — decided today to extend this to a 2-day effort (was previously a single 31 Aug entry). Calendar Hard Milestone updated accordingly. Site visit timing under ambiguity as of the 3 Aug BOQ gap meeting — regardless, need white-box photos ready and a post-site-survey deliverable prepared. Update 7 Aug: this is now a settled decision, not just under review — re-scoped from a technical review to a client-facing "show face" meeting, relying on the site team (not a technical review team) for measurements.
36 | 2026-08-04 | Schedule and prepare for the K5M FFE SHD01 review meeting (5 Aug, 10:30am) | FFE SHD | 1 | Meeting online |  |  | Done | 2026-08-05 | Per 4 Aug meeting with Claire. Ensure consolidated feedback ready before the meeting; prepare/circulate latest drawings. The Shop Drawing Tracker (once built) will serve as the meeting agenda — no separate agenda doc planned. Meeting held 5 Aug as scheduled. MOM to follow — see new row below; content still pending from Shagun as of 6 Aug.
37 | 2026-08-04 | Connect with Resti as soon as possible to flag current K5M technical support needs | WDCO Internal Project Management | 1 | Meeting online | Resti |  | Done |  | Resti is the new Head of Engineering (joined 2026-08-04) — technical point of reference for shop drawings/engineering support across all projects, working with Tharusha (draftsman). Per his introduction: connect early so he can prioritize. Connected — Resti has already completed the stone arch BOQ gap calculation requested (see new row below).
38 | 2026-08-06 | Clearly document Resti's completed stone arch BOQ gap calculation and incorporate it into the existing scope-gap findings | Project Scope | 1 | Documentation | Resti |  | Done |  | Per 3 Aug BOQ gap meeting decision (a). Resti's raw calculation is complete (see row above) — this is writing it up clearly. References meetings/260803_K5M_Meeting_BOQ_Scope_Gap/post-meeting/Fit-out BOQ Scope Gap/stone_arch_findings.md. Done — reconciliation table rebuilt with Resti's numbers, confirmed by his clarifications (door-jamb depth doesn't affect the calc method; client's margin practice explains the 6&7 gap, mirrored into 1&2). All arches now resolved except the second banquette arch (confirmed not covered by any BOQ line).
39 | 2026-08-06 | Draft and send an email covering all BOQ changes (the gap, the difference) to Filippo Sona to handle from there | Communication Management - Internal | 1 | Send an email | Filippo Sona |  | Done |  | Per 3 Aug BOQ gap meeting decision (b). Filippo Sona is WDCO's co-founder and main partner — internal, not client-facing. Done — sent 6 Aug ("K5M ¦ BOQ Gap / Variables since Kick Off"), confirmed via mailbox review 7 Aug.
40 | 2026-08-06 | Email Maria for container requirements so the container can be scheduled right away | Logistics | 1 | Send an email | Maria |  | Done |  | Per 3 Aug BOQ gap meeting decision (c). Maria is WDCO's logistics personnel, handling container booking etc. Done — sent 7 Aug to Maria Al Balushi with real numbers: ~30 pieces for one room, target departure window 5-10 Oct, 10 Oct hard deadline. Full weight/size estimate still promised for end of August.
41 | 2026-08-06 | Build a new Fitout Scope document — clearly defining everything, with a "Doubts" section for anything removable/uncertain | Project Scope | 1 | Documentation |  |  | To Do |  | Per 3 Aug BOQ gap meeting decision (d). This resolves Hard Rule 14's long-pending Fitout base-scope file once built — update that rule once done.
42 | 2026-08-06 | Schedule a fitout scope meeting with H&T ASAP | Fitout SHD | 1 | Meeting online | H&T |  | To Do |  | Per 3 Aug BOQ gap meeting decision (e).
43 | 2026-08-06 | Confirm with Ariel which fitout drawings are shareable | Fitout SHD | 1 | Follow up email | Ariel |  | Done | 2026-08-07 | Per 3 Aug BOQ gap meeting decision (f). Deadline of 7 Aug confirmed by Ariel. Done — Ariel delivered A4 layout drawings via WeTransfer, 7 Aug.
44 | 2026-08-06 | Send MOM from the internal FFE Shop Drawing (SHD01) review meeting held 5 Aug | FFE SHD | 1 | Documentation |  |  | To Do | 2026-08-06 | Per 3 Aug BOQ gap meeting decision (j). Going forward, SHD review meeting minutes will be traced via the Shop Drawing Tracker itself rather than a separate MOM doc — content for this specific MOM still pending from Shagun as of 6 Aug.
45 | 2026-08-06 | Develop a swatch sample-box presentation concept and show Khamille to decide how to move forward | Material Package FFE | 1 | Documentation | Khamille |  | To Do | 2026-08-06 | Per 4 Aug meeting with Khamille — swatch quantities/sizes agreed (already shared with H&T, see Dev Log); spans both FFE and Fitout material packages. Decision on presentation approach expected by 7 Aug.
46 | 2026-08-06 | Compile all compliance documents received into a single consolidated record | Compliance Collection | 2 | Documentation |  |  | To Do |  | Per 3 Aug BOQ gap meeting. Ties to row above (Abdellatif compliance docs, target close 10 Aug).
47 | 2026-08-06 | Install/authorize the MCP connector so Woody can read Shagun's Outlook inbox (read-only — no send capability) | WDCO Internal Project Management | 1 | Documentation |  |  | To Do | 2026-08-07 | Per #newtask. Type of Task guessed (Documentation) — doesn't cleanly fit the 7 categories, same issue as the SketchUp task. Depends on Shagun completing /mcp authorization herself. Feeds the new #GoodMorning/#checkmail mail-check design (see Command Center). Tested via the outlook-email-drafter connector (authenticated fine) — hit a hard tenant-level block: Access to OData is disabled, blocked by tenant Application Access Policy. This needs Wood Couture IT/M365 admin to exempt this app or grant mail-read consent at the admin level — not something fixable via personal authorization.
48 | 2026-08-06 | Extend the Task Tracker's dropdown data validation (Umbrella Task/Priority/Type of Task/Status columns) beyond row 33 — every row added since (34 onward, including today's) has no validation at all | WDCO Internal Project Management | 3 | Documentation |  |  | To Do |  | Found during #totalcheck, 6 Aug, while fixing an invalid "Blocked" status value that the dropdown should have caught but didn't. Low priority — cosmetic/preventative, not blocking anything today.
49 | 2026-08-07 | Reconcile the internal working schedule against the actual contractual mock-up deadline (30 Nov 2026, per the original award letter) with Filippo/Claire — the internal schedule appears to have drifted past it | Contractual - Client Facing | 1 | Meeting online | Filippo Sona | Claire | To Do |  | Surfaced via full mailbox review, 7 Aug. Filippo cited 30 Nov as the hard contractual milestone in a live liability-negotiation email with the client; internal planning has since referenced 20 Dec. Needs reconciling, not just tracking forward.
50 | 2026-08-07 | Chase H&T on the sample box (due 8 Aug) — escalate per the Plan-B threat already given if it slips | Material Package FFE | 1 | Follow up email | H&T |  | To Do | 2026-08-08 | Shagun already put H&T on notice 6 Aug: if the 8 Aug date can't be held, escalate to management and source samples elsewhere, with H&T then required to match approved samples exactly.
51 | 2026-08-07 | Confirm H&T has remade the metal samples produced in the wrong size | Material Package FFE | 1 | Follow up email | H&T |  | To Do |  | Flagged 6 Aug — metal samples came back in the wrong dimensions against the confirmed sizes (Fabric/Wood/Glass 14x10cm, Metal 10x7cm).
52 | 2026-08-07 | Follow up with Adil Mokaddem on the corrupted/incomplete DWG file (plan numbers ET01-T1B1-SDB-100 through 150) | RFI - Client | 1 | Follow up email | Adil |  | To Do |  | RFI sent 7 Aug ("WDCO K5M ¦ PH T1B1 ¦ RFI ¦ Problem with DWG File"); architect's fix still pending as of the mailbox review.
53 | 2026-08-07 | Follow up with Adil Mokaddem on structural reinforcement provisions for the fit-out (ceiling supports/backing around wardrobe and fitted-sofa areas), incl. recent site photos | Fitout SHD | 2 | Follow up email | Adil |  | To Do |  | Requested 4 Aug, no reply captured as of 7 Aug mailbox review.
54 | 2026-08-07 | Confirm wall art specification and art-consultant point of contact with the client | RFI - Client | 2 | Follow up email | Abdellatif Menbar |  | To Do |  | Requested 6 Aug, referencing G&B's earlier advice to coordinate with the project's art consultant — contact still unconfirmed.
55 | 2026-08-07 | Raise the PO for Ariel's drafting invoice (USD 720, 72 pages reformatted to A4) | WDCO Internal Project Management | 2 | Documentation | Ariel |  | To Do |  | Quote accepted in principle 4 Aug; PO not yet raised as of 7 Aug mailbox review.
56 | 2026-08-07 | Track H&T capacity/responsiveness risk — factory completion now flagged for 16 Aug (was believed already in preparation), competing for capacity against another WDCO project (2576-F) | Communication Management - Production Partner | 1 | Meeting online | H&T |  | To Do |  | Khamille's high-importance flag, 7 Aug: "the dates and info we're getting keep shifting, and it's getting hard to plan around." Same underlying H&T issue as the sample-box escalation above — treat together.
57 | 2026-08-07 | Check resolution status of the table stability defect on T1B1-BR-CG-03 (base too narrow, CTO recommended ≥36cm base) | FFE SHD | 2 | Follow up email | Fabrizio |  | To Do |  | Flagged by Fabrizio Pensalfini in mid-July; resolution status not visible in the mailbox review — worth a direct check.

## Change Log
Date | Sheet | Change | Done By
2026-08-07 | All | Merged Task Tracker and Project Calendar into one workbook. Added Task Number <-> Calendar link mechanism (Logged on Calendar? column on Task Tracker; #TaskNumber tag + HYPERLINK convention for Calendar entries going forward). | Claude