## FFE Materials
K5M — FFE MATERIAL PACKAGE
As of 27 July 2026 — first version. FFE and Fit-out are tracked in entirely separate files; never merge with the Fit-out Material Package.
STATUS
A | Approved
B | Approved with comments
C | Rejected
S | Submitted
T | To be Submitted
O | Omitted
Colors for "Approved with comments" and "Submitted" are a proposed extension of the official Brand DNA status palette (only Approved/Rejected/To be Submitted/Under Review/No Control Sample have official colors) — confirm or replace.
No. | Material Code | Thumbnail | Category | Description (FR) | Description (EN) | Finish / Vernish | Finish Type | Base Colour (if Compound) | Applied Process (if Compound) | Item Code (WDCO) | Control Sample (Y/N) | High-Res Available (Y/N) | High-Res Link | Status | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | Remarks / Open Issues
1 | FFE-WD-01 |  | Wood | Noyer | Walnut | Teinté satiné / Tinted satinated | Single |  |  | K5M-T1B1-CHA-BE-01 | N | Y | [7 empty] | Bed base structure
2 | FFE-WD-01 |  | Wood | Noyer | Walnut | Teinté satiné / Tinted satinated | Single |  |  | K5M-T1B1-CHA-BE-01(B) | N | Y | [7 empty] | Headboard lateral panels — color must match FFE-WD-02
3 | FFE-WD-01 |  | Wood | Noyer | Walnut | Teinté satiné / Tinted satinated | Single |  |  | K5M-T1B1-CHA-CS-01 | N | Y | [7 empty] | Console structure
4 | FA-03 |  | Fabric | LI 872 02 Flots nacreux | LI 872 02 Flots nacreux (Elitis) |  | Single |  |  | K5M-T1B1-CHA-BE-01 | Pending | N | [7 empty] | Bed spring-box fabric; sample sent by Elitis 21 Jul, no further update logged since
5 | FA-02 |  | Fabric | 2946-A black (Naturtex) | 2946-A black (Naturtex) | Teinte Saule de G&B | Single |  |  | K5M-T1B1-CHA-BE-01(B) | N/A | N/A | [7 empty] | Headboard center panel — in-house G&B production, cannot source from an external supplier (dead end, confirmed in fabric tracker)
6 | FFE-ME-02 |  | Metal | Laiton martelé, patiné noir | Hammered brass, dark patinated | Patiné noir / Dark patinated | Compound | Dark patina (match FFE-ME-01) | Hammered (martelé) | K5M-T1B1-CHA-BE-01(B) | N | Y | [7 empty] | Headboard frame
7 | FFE-ME-07 |  | Metal | Métal patiné noir | Metal dark patinated |  | Single |  |  | K5M-T1B1-CHA-BT-01 | N | N | [7 empty] | Bedside table (CG01) legs; patina must visually match FFE-ME-01 per G&B note; material reference still missing
8 | FFE-ST-02 |  | Stone | Calacatta Oro | Calacatta Oro | Honed / Adouci | Single |  |  | K5M-T1B1-CHA-BT-01 | N | N | [7 empty] | Bedside table top/shelf; sample still to be provided by supplier
9 | FFE-ST-01 |  | Stone | Taj Mahal (anciennement Onyx miel) | Taj Mahal (was Onyx Honey) | Honed / Adouci | Single |  |  | K5M-T1B1-CHA-CS-01 | N | N | [7 empty] | Console top; SUBSTITUTED from Onyx Honey to Taj Mahal per 21 Jul 2026 material list update — sample still to be provided by supplier
10 | FFE-WD-02 |  | Wood | Chêne teinté fumé brossé | Smoked tinted brushed oak | Légèrement satiné | Single |  |  | K5M-T1B1-CHA-RT-01 | N | Y | [7 empty] | Small round table barrel/belt — color must match FFE-WD-01
11 | FFE-ST-04 |  | Stone | Alabaster | Alabaster |  | Single |  |  | K5M-T1B1-CHA-RT-01 | N | N | [7 empty] | Small round table top
12 | FFE-GL-02 |  | Glass | Verre ambré texturé | Amber textured glass |  | Single |  |  | K5M-T1B1-CHA-WS-01 | N | Y | [7 empty] | Bedroom sconce (LT01) panels
13 | FFE-ME-07 |  | Metal | Métal patiné noir | Metal dark patinated |  | Single |  |  | K5M-T1B1-CHA-WS-01 | N | N | [7 empty] | Bedroom sconce (LT01) structure
14 | FFE-ME-08 |  | Metal | Bronze patiné noir | Bronze black patinated |  | Single |  |  | K5M-T1B1-CHA-TL-01 | N | Y | [7 empty] | Bedside table lamp (LT03) barrel
15 | FA-07 |  | Fabric | Gabor 001 avorio (Dedar) | Gabor 001 avorio (Dedar) |  | Single |  |  | K5M-T1B1-CHA-TL-01 | Y | Y | [7 empty] | Bedside lamp shade; sample RECEIVED from Dedar 23 Jul 2026 — image sourced by us directly from Dedar, not client-provided
16 | PP-01 |  | Fabric | Tiverton border 19mm (Samuel & Sons) | Tiverton border 19mm (Samuel & Sons) |  | Single |  |  | K5M-T1B1-CHA-TL-01 | Open decision | Y | [7 empty] | Lampshade trim; Samuel & Sons refused a free sample — OPEN DECISION: pay for 1 ML or not (your call). Product image sourced by us directly.
17 | FFE-ME-07 |  | Metal | Métal patiné noir | Metal dark patinated |  | Single |  |  | K5M-T1B1-CHA-SL-01 | N | N | [7 empty] | Stool (SE02) structure
18 | FA-06 |  | Fabric | A-768 (Naturtex) | A-768 (Naturtex) |  | Single |  |  | K5M-T1B1-CHA-SL-01 | Pending | Y | [7 empty] | Stool seat; referred to Warps & Wefts (Naturtex ME rep), awaiting sample/stock/pricing. Image sourced by us directly.
19 | FFE-WD-02 |  | Wood | Chêne teinté fumé brossé | Smoked tinted brushed oak | Légèrement satiné | Single |  |  | K5M-T1B1-CHA-AC-01 | N | Y | [7 empty] | Armchair structure
20 | FA-10 |  | Fabric | "Caoutchouc grainé" cuir (G&B) | "Caoutchouc grainé" leather (G&B) |  | Single |  |  | K5M-T1B1-CHA-AC-01 | N | N | [7 empty] | Armchair upholstery; G&B in-house material, sourcing status not yet logged in fabric tracker
21 | FFE-ME-09 |  | Metal | Métal perforé | Perforated metal |  | Single |  |  | K5M-T1B1-ENT-WS-01 | N | Y | [7 empty] | Entrance sconce (LT01) shade
22 | FFE-ME-01 |  | Metal | Laiton patiné | Patinated brass |  | Single |  |  | K5M-T1B1-ENT-WS-01 | N | N | [7 empty] | Entrance sconce (LT01) ring/structure; G&B VE suggestion to combine with FFE-ME-07 (same patina family) — not yet decided
23 | FFE-WD-02 |  | Wood | Chêne teinté fumé brossé | Smoked tinted brushed oak | Légèrement satiné | Single |  |  | K5M-T1B1-ENT-MR-01 | N | Y | [7 empty] | Entrance mirror (MR02) frame
24 | FFE-GL-01 |  | Glass | Miroir extra-clair | Extra clear mirror | Extra clair / Extra clear | Single |  |  | K5M-T1B1-ENT-MR-01 | N/A | N/A | [7 empty] | Entrance mirror (MR02) glass — classical extra-clear mirror, reference not required per G&B
25 | FFE-ME-08 |  | Metal | Bronze patiné noir | Bronze black patinated |  | Single |  |  | K5M-T1B1-SDB-ST-01 | N | Y | [7 empty] | Bathroom side table (SDB CG02) — all-in this material
26 | FA-11 |  | Fabric | "Angora grainé" cuir (G&B) | "Angora grainé" leather (G&B) |  | Single |  |  | K5M-T1B1-SDB-PF-01 | N | N | [7 empty] | Bathroom pouf (SDB SE01) upholstery; G&B in-house material, sourcing status not yet logged
27 | PP-02 |  | Fabric | Franges torse 120mm 33227-9826 (Houlès) | Bullion fringe 120mm 33227-9826 (Houlès) |  | Single |  |  | K5M-T1B1-SDB-PF-01 | In transit | Y | [7 empty] | Bathroom pouf fringe trim; sample courier in transit as of 24 Jul, tracking EMX 1000044713333. Image sourced by us directly.
EXCLUDED — not used in any K5M FFE product (kept out of the working list; still fully documented in 002_knowledge-bank/materials/T1B1_material_cross_reference.md)
FFE-GL-03, FFE-GL-04, FFE-ME-03, FFE-ME-04, FFE-ME-05, FFE-ME-06, FFE-ST-03, FFE-ST-05, FFE-WD-03, FFE-OT-01, FFE-OT-02, FFE-OT-03