## Task Tracker
| 1 | Important and urgent
| 2 | Urgent but not important
| 3 | Important but not urgent
| 4 | Neither — just needs a place to live
S.No. | Date Raised | Task | Umbrella Task | Priority | Type of Task | Dependent On 1 | Dependent On 2 | Status | Due/Target Date | Note
1 | 2026-07-29 | Discuss with Claire — Material Package packaging (Claire vs Khamille) | Material Package FFE | 3 | Meeting physical | Claire |  | Done |  | Resolved via 29 Jul MoM.
2 | 2026-07-29 | Follow up with Khamille on sample presentation format & timeline | Material Package FFE | 1 | Follow up call | Khamille |  | To Do |  | Per 29 Jul MoM — explicitly flagged High priority, must not slip.
3 | 2026-07-29 | Discuss with Claire — fit-out substructure requirement approach | Fitout SHD | 2 | Meeting physical |  |  | To Do |  | Not explicitly closed by the 29 Jul MoM — confirm still open.
4 |  | Send K5M "The Client" substrcture requirements for the fitout | RFI - Client | 1 |  | H&T |  | To Do | 2026-08-05 | Due date corrected 31 Jul (was 05/09/2026, a month off) — matches the 5 Aug Calendar milestone and the urgency flagged in this week's risk-mitigation note: implementation cannot start until this is sent.
5 |  | Get Fitout Specification Drawings ready for supplier review / talk to Ariel about scaling and improving the fit-out drawing | Fitout SHD | 1 | Follow up email | Ariel |  | In Progress |  | Sent Ariel all details. Claire has asked to pause — new team joinee starts Monday (3 Aug); will assess if he can take this on before deciding who owns the work.
6 | 2026-07-29 | Build project contact sheet (security log) | Communication Management - Internal | 1 | Documentation |  |  | Done
7 | 2026-07-29 | Close the BOQ gap problem / Fit-out scope | Project Scope | 1 | Meeting physical |  |  | In Progress | 2026-08-03 | Stakeholder meeting scheduled Monday per 29 Jul MoM; no scope additions until then. Agenda topics confirmed 30 Jul: stone arch over wardrobe and fitted sofa, suspended glass light over the basin, fittings — hardware & bathroom. See meetings/260803_K5M_Meeting_BOQ_Scope_Gap/pre-meeting/agenda.md.
8 | 2026-07-29 | Fix a meeting with H&T — Material Package briefing | Material Package FFE | 2 | Meeting online |  |  | Done | 30th July | Meeting set at 10 am
9 | 29th july | Make an agenda for the HT material package review meeting. | Communication Management - Production Partner | 2 | Documentation |  |  | Stale | 29th july | Superseded — H&T Material Package review meeting already happened (30 Jul, 10am). Marked Stale + hidden by Woody during #totalcheck.
10 | 2026-07-29 | Form a central RFI tracking/management system within git | RFI - Internal | 3 | Documentation |  |  | To Do |  | Merged with former row 22 (duplicate ask) on 30 Jul per Shagun.
11 | 2026-07-30 | Brief H&T on fit-out scope and drawings + consolidated info request (substructure, sample drawings, technical data sheets) | Fitout SHD | 1 | Send an email |  |  | To Do | 2026-07-30 | Per 29 Jul MoM: one consolidated email, not sequential individual requests. Due today.
12 | 2026-07-30 | Finish the AI-created COC and shift to OneDrive to maintain from there | COC Management | 2 | Documentation |  |  | In Progress
13 | 2026-07-30 | Finish formatting the Project Calendar and Task Tracker, and move both to OneDrive to maintain from there | WDCO Internal Project Management | 1 | Documentation |  |  | In Progress | 2026-07-30 | Merged with former row 24 (duplicate ask) on 30 Jul per Shagun. Aesthetic alignment pass by Shagun, then final push to OneDrive.
14 | 2026-07-30 | Collate feedback on FFE SHD00 to start work on SHD01 | FFE SHD | 2 | Documentation |  |  | To Do
15 | 2026-07-30 | Fitout Fabrics — banquette fabric sheet — check with suppliers for samples | Material Package Fitout | 3 | Follow up email |  |  | In Progress |  | Per 31 Jul H&T meeting — Fit-out fabrics partially researched online, findings updated in the Excel sheet and fabric folder shared.
16 | 2026-07-30 | Create a Google SketchUp model for the project briefing | WDCO Internal Project Management | 1 | Arranging |  |  | In Progress | 2026-08-02 | Hoped for before Monday's meeting — Type of Task guessed, doesn't cleanly fit the 7 categories.
17 | 2026-07-30 | Add fitted-sofa client sample request to fabrication schedule and arrange sample | Material Package Fitout | 2 | Arranging |  |  | To Do |  | Per 29 Jul MoM.
18 | 2026-07-30 | Send WDCO project information to the new lighting designer | Communication Management - Client | 1 | Send an email |  |  | Done | 2026-07-30 | Introduction email sent 30 Jul. Still need the designer's actual name/email for CONTACT_SHEET.md.
19 | 2026-07-30 | Follow up with Victoire on glass sample GL-3A for better specification clarity | Material Package FFE | 3 | Follow up email |  |  | To Do |  | Per 29 Jul MoM.
20 | 2026-07-30 | Raise an RFI with the lighting designer | RFI - Client | 1 | Send an email |  |  | In Progress | 2026-08-06 | Email sent 30 Jul referencing the existing FF&E lighting RFI (Sheet 3, 'Lighting / Lighting Equipment Only RFI') — requested equipment details/compliance clarifications from Gisela. Recipient confirmed as the same Gisela Steiger already in CONTACT_SHEET.md, not a new contact. Awaiting her reply; must close by 6 Aug.
21 | 2026-07-30 | Follow up with Gisela — structured Fit-out RFI list and workflow | RFI - Client | 2 | Send an email |  |  | To Do | 2026-08-06 | Committed to this in the 30 Jul status email — 'by next week I should be able to share a clearer RFI list and workflow.'
22 | 2026-07-30 | Create a central RFI tracking system within git | RFI - Internal | 3 | Documentation |  |  | Stale |  | Merged into row 10 (duplicate) — marked Stale + hidden by Woody, 30 Jul.
23 | 2026-07-30 | Prepare agenda for BOQ scope gap meeting (Monday, 3 Aug) | Project Scope | 1 | Documentation |  |  | Done | 2026-07-30 | Agenda covers: stone arch over wardrobe/fitted sofa, suspended glass light over basin, hardware & bathroom fittings. Stored at meetings/260803_K5M_Meeting_BOQ_Scope_Gap/pre-meeting/agenda.md.
24 | 2026-07-30 | Finish formatting the Project Calendar and Task Tracker to shift both to OneDrive | WDCO Internal Project Management | 1 | Documentation |  |  | Stale | 2026-07-30 | Merged into row 13 (duplicate) — marked Stale + hidden by Woody, 30 Jul.
25 | 2026-07-30 | Reply to Valentine (design team) with material package sample photos, if not resolved in today's H&T meeting | Material Package Fitout | 2 | Send an email | H&T |  | To Do | 2026-07-30 | Contingent on today's 10am H&T Material Package review — reply directly to Valentine by 1pm today if not addressed there.
26 | 2026-07-30 | Decide redaction scope for real client/Production Partner names found in README.md, PROJECT_BRIEFING.md, SESSION_START.md, and DAILY_LOG.md (main branch) | WDCO Internal Project Management | 3 | Documentation |  |  | To Do |  | Flagged while building HARD_RULES.md — Shagun asked to hold off deciding scope (fix living docs only vs. also rewrite DAILY_LOG history vs. keep Wood Couture as-is). Revisit when ready.
27 | 2026-07-31 | Align all product codes across trackers (Material Package, COC Master Scope, client-facing documents) — especially client-facing product codes | COC Management | 1 | Documentation |  |  | In Progress |  | FFE scope codes now aligned (CH→CHA fixed 31 Jul in the canonical Master SKU List). Material Package’s own CHA-RT-01 error still unfixed there (Shagun deferred that edit). Fitout scope not yet confirmed — expected next week; recheck fitout codes once that lands.
28 | 2026-07-31 | Decide and inform Woody which project scope file(s) will be the base/authoritative source for all documents going forward | COC Management | 1 | Documentation |  |  | In Progress |  | FFE resolved 31 Jul — holy grail file confirmed: 260724_WDCOK5M_FFE_Master SKU List.xlsx (OneDrive, 00_SHARED/Project Scope). Now added to HARD_RULES.md. Fitout base scope file still pending — Shagun expects to confirm next week.
29 | 2026-07-31 | File H&T Meeting Minutes (MOM, 31 Jul — material package development) into the repo meeting folder | Communication Management - Production Partner | 2 | Documentation |  |  | Done | 2026-07-31 | Filed at meetings/260731_K5M_Meeting_H&T_Material_Package/minutes/. Not a duplicate of the #projectdevelopment Dev Log entries — those capture the narrative, this is the source document.
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: They are all interdependent, how do we track that?