## Sheet1
K5M INTERNAL MEETING | [5 empty] | DATE : 03.08.2026
For : FFE | WDCO | Production Partner | Client Side
|  |  | Client Rep | Design Team | Architect | Lighting Designer
Project Scope | Locked | Locked | Locked | Locked | Locked | 6th Aug
Project Brief to Production Partner | Locked | Locked | NA | NA | NA | NA
Material Package Brief | In Progress | In Progress | Locked | Locked | Locked | NA
Material Package Development | In Progress | In Progress | Awaiting | Awaiting | Awaiting | Awaiting
Shop Drawing 00 | Locked | Locked | Locked | Locked | NA | 6th Aug
Shop Drawing 01 | In Progress | Awaiting | 20th August | 20th August | 20th August | NA
On Site Cordination | 31st Aug | 31st Aug | 31st Aug | NA | 31st Aug | NA
RFI - Open with Client | NA | NA | 1 | 0 | 0 | 0
RFI - Open Internally (WDCO Only) | 0 | NA | NA | NA | NA | NA
RFI - Open with production partner | NA | 1 | NA | NA | NA | NA
For : Fitout | WDCO | Production Partner | Client Side
|  |  | Client Rep | Design Team | Architect | Lighting Designer
Project Scope | On Hold | Behind | Locked | Locked | Locked | NA
Project Brief to Production Partner | On Hold | Behind | Locked | Locked | Locked | NA
Material Package | Locked | Locked | Locked | Locked | Locked | NA
Material Package Development | In Progress | In Progress | Awaiting | Awaiting | Awaiting | Awaiting
Shop Drawing 00 | Behind | Behind | NA | NA | NA | NA
Shop Drawing 01 | Not Started Yet
On Site Cordination | On Hold
RFI - Open with Client | NA | NA | 1 | 0 | 1 | Behind
RFI - Open Internally (WDCO Only) | 4 | NA | NA | NA | NA | NA
RFI - Open with production partner | NA | 1 | NA | NA | NA | NA
RFI - Open Internally (WDCO Only) | Status
Review of SHD00 Feedback | Current : Make the updated feedback tracker, show claire and proceed from there
31st August Visit Planning | Behind
Fitout Drawings - SHD00 | Behind , But awaiting new joinee, should start by today
Substructure Fitout | Behind , awaiting resolution on project scope
Agenda for Meeting Today : 03.08.2026 | Resolution
1. Fitout Scope
A.Stone Archs in T1B1 Entrance
B.Stone Archs in T1B1 Chamber
C. Suspended Lights over basin
D.Hardware & Bathroom Fitting
E.Blinds
F.Wallpaper**
Legend | Meaning
Locked | Task Closed Positively for now
In Progress | Developing as expected
On Hold / Behind | Open Risk
Deadline
Daily Follow Up.
Work hasn’t started yet but we are not late either